## Sheet1
Straw Chambers | start date | end date | M&S or Labor | Cost | BOE | split
[6 empty] | M&S | Labor
Send out orders for straws, wire, connector pins, gas manifolds, ABS endcaps, and gas systems | 2016-07-01 | 2016-10-29 | M&S | 317111 | Quotes + Estimates from PANDA | 317111
Design PCBs for Readout and HV | 2016-07-01 | 2016-08-30 | Labor | 0 | E-Shop
Purchase PCB components and manufacture bords | 2016-09-01 | 2016-10-31 | Both | 10000 | E-Shop + Students | 5000 | 5000
Design Large Chamber Mounting | 2016-07-01 | 2016-08-30 | Labor | 5000 | Estimate from similar projects (Designer) |  | 5000
Manufature Straws | 2016-09-01 | 2017-09-01 | Labor |  | Students+Tech
Machining of Chamber Mountings (Chambers 2-4) | 2017-10-01 | 2017-11-30 | Labor | 5000 | Machine Shop |  | 5000
Mount and Test Chambers 2-4 | 21/1/17 | 2017-10-31 | Labor |  | Students+Tech
Ship Chambers to PSI | 2017-11-01 | 2017-12-01 | Both | 4000 |  | 3000 | 1000
Commision Chambers 2-4 at PSI | Test Beam | Test Beam | Labor |  | Students
[6 empty] | 325111 | 16000
Formulas:
end date = [start date]+120