## Sheet1
WBS 5 | Cryogenic Hydrogen Target | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE (labor is max estimated requirement for task) | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | Total | Status
5.1 | Bring Cryolab to Safe Operating State | 2014-03-01 | 2014-06-01 | Both | 18000 | 5000 | 2000 | Internal University Proposal | GWU | 0 | 0 | 25000 | 0 | Done
5.1.1 | Conceptual Design | 2015-06-01 | 2015-12-31 | Labor | 0 | 40000 | 0 | Average Cost to Other Projects | DOE | 40000 | 0 | 40000 | 40000 | Done
5.1.1a | Engineering Drawings | 2016-06-01 | 2017-03-01 | Labor | 0 | 40000 | 14000 | Based on Conceptual Design one month PI | DoE | 54000 | 14040
5.1.2 | Order Instrumentation, Hardware, and Monitoring Devices | 2016-07-01 | 2016-09-01 | Both | 135000 | 0 | 2500 | Adjusted Cost based on other recent projects two weeks post doc | NSF/DOE | 137500 | 35750 | price fluctuations | 173250
5.1.3 | Order Cryopump - Cold Head | 2017-07-01 | 2017-08-01 | Equipment | 30000 | 0 | 1250 | Internet Price Listings and adjusted cost to other recent projects - one week Postdoc asking for quotes | NSF/DOE | 31250 | 8125 | price fluctuations - design variation | 39375
5.1.4 | Order Components of Motion System | 2017-01-01 | 2017-03-01 | Equipment | 35000 | 0 | 2500 | Adjusted costs from other recent projects two week post doc | NSF/DOE | 37500 | 9750 | price fluctuations - design variation | 47250
5.1.5 | Order Material/Supplies for Scattering Chamber, Cell, Target Ladder, Holders and Railings | 2017-01-01 | 2017-02-01 | M&S | 14000 | 0 | 2500 | Adjusted costs from other recent projects two weeks Postdoc | NSF/DOE | 16500 | 4290 | price fluctuations - design variation | 20790
5.1.6 | Prototype Cells and Cell Holders Machining and Assembly | 2017-01-01 | 2017-03-01 | Labor | 0 | 9600 | 6000 | 160 hrs $60/hrs =$9,600 Machinist ---two months each Postdoc and Students | NSF/DOE | 15600 | 4056 | price fluctuations - design variation | 19656
5.1.7 | Build Test Stand Chamber | 2017-01-01 | 2017-02-01 | Labor | 0 | 4800 | 6000 | 80 hrs $60/hrs =$4,800 Machinist ---one month each Postdoc and Students | NSF/DOE | 10800 | 2808 | price fluctuations - design variation | 13608
5.1.8 | Pressure, Vacuum, Destructive Tests of Cell Prototypes | 2017-06-01 | 2017-02-01 | Labor | 0 | 0 | 12000 | Two months each for Postdoc, Students | NSF/DOE | 12000 | 2760 |  | 14760
5.1.9 | Evaluation - Design Modification | 2017-02-01 | 2017-03-01 | Labor | 0 | 0 | 6000 | One month each for Postdoc, Students | NSF/DOE | 6000 | 1380 |  | 7380
5.1.10 | Prototype of Modified Cells | 2017-03-01 | 2017-04-01 | Labor | 0 | 4800 | 1750 | 80 hrs $60/hrs =$4800 Machinist ---one week each Post Doc and Students | NSF/DOE | 6550 | 1703 |  | 8253
5.1.11 | Second Round of Tests - Cold Test of Cells | 2015-03-01 | 2015-04-01 | Labor | 0 | 0 | 6000 | One month each Post Doc and Students | NSF/DOE | 6000 | 1380 |  | 7380
5.1.13 | Final Review of Design and Modifications | 2015-04-01 | 2015-05-01 | Labor | 0 | 2400 | 6000 | 40 hrs $60/hrs =$2400 Machinist ---one month each Post Doc and Students | NSF/DOE | 8400 | 1932 |  | 10332
5.1.14 | Construction of Scattering Chamber | 2017-04-01 | 2017-07-01 | Labor | 0 | 9600 | 6000 | 160 hrs $60/hrs =$9,600 Machinist ---one month each Postdoc and Students | NSF/DOE | 15600 | 4056 | price fluctuations - design variation | 19656
5.2.1 | Construction of Cells | 2017-04-01 | 2017-07-01 | Labor | 0 | 9600 | 6000 | 160 hrs $60/hrs =$9600 Machinist ---one month each Postdoc and Students | NSF/DOE | 15600 | 4056 | price fluctuations - design variation | 19656
5.2.2 | Tests of Cells and Scattering Chamber | 2017-07-01 | 2017-09-01 | Labor | 0 | 0 | 12000 | Two months each Post Doc and Students | NSF/DOE | 12000 | 2760 |  | 14760
5.2.3 | Evaluation - Modifications | 2017-09-01 | 2017-10-01 | Labor | 0 | 4800 | 6000 | 80 hrs $60/hrs =$5,000 Machinist ---one month each Post Doc and Students | NSF/DOE | 10800 | 2484 |  | 13284
5.2.4 | Second Round of Tests of Scattering Chamber and Cells Including motion test and test of emergency conditions | 2017-10-01 | 2017-12-01 | Labor | 0 | 0 | 6000 | One month each Post Doc and Students | NSF/DOE | 6000 | 1380 |  | 7380
5.2.5 | Evaluation and Readiness Review | 2017-12-01 | 2017-01-01 | Labor | 0 | 0 | 6000 | One month each Post Doc and Students | NSF/DOE | 6000 | 1380 |  | 7380
5.2.6 | Construct Boxes for Shipping and Packing | 2017-12-01 | 2017-12-31 | Both | 1000 | 2000 | 1750 | 40 hrs Carpentry Shop -- One week each Postdoc and Students | NSF/DOE | 4750 | 1235 | price fluctuations - design variation | 5985
5.2.7 | Shipping, Receiving and Unpacking | 2018-01-01 | 2018-02-01 | Both | 2000 | 0 | 3500 | Two weeks each Postdoc and Students | NSF/DOE | 5500 | 1430 | price fluctuations | 6930
5.2.8 | In Situ Assembly and Testing | 2018-02-01 | 2018-04-01 | Labor | 0 | 0 | 6000 | One month each Post Doc and Students | NSF/DOE | 6000 | 1380 | design variation - unforseen needs | 7380
5.2.9 | PSI Safety Engineering Review and Modifications to Make Compliant | 2018-04-01 | 2018-05-01 | Labor | 0 | 0 | 6000 | One month each Post Doc and Students | NSF/DOE | 6000 | 1380 | design variation - unforseen needs | 7380
5.3 | Turn over to PSI | 2018-05-01 | 2018-06-01 | Labor | 0 | 0 | 6000 | One month each Post Doc and Students | NSF/DOE | 6000 | 1380 |  | 7380
|  |  |  | cost to project | 217000 | 87600 | 131750 |  |  | 436350 | 110895 | Does not include Travel, Fringe and imdirects | 547245
|  |  |  | Equipment -> no IDC | 214000 |  | Total Labor | 219350
|  |  |  | M&S -> | 3000 |  | F&A on Labor | 115158.75 | 334508.75 | Labor+F&A
|  |  |  | IDC -> | 1575 |  | Contingency on labor +FandA | 76937.0125 |  |  |  | Total W/O contingency | 652295.4463
|  |  |  | total M&S | 217000 | [6 empty] | Total Without Travel | 813611.9587
[7 empty] | total f&A | 116733.75 |  |  |  | Total with travel | 828861.9587
[7 empty] | total cont. | 176566.5125
[12 empty] | Contingency | 176566.5125
|  |  |  | Major Comp | 214000 |  | Fringe | 55056.85 | Travel | 10000
|  |  |  | F&A | 0 |  | ID Fringe | 28904.8462 | ID Travel | 5250
|  |  |  | Cont | 49220 |  | FB+ID | 83961.6962 |  | 15250
|  |  |  | other M&S | 3000
|  |  |  | F&A | 1575
|  |  |  | Cont | 1189.5
|  |  |  | Total M&S | 217000
|  |  |  | F&A | 1575 | 116733.75 | Total F and A
|  |  |  | Tota Cont | 50409.5