## SiPM
WBS 2 | Beam Cerenkov part | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | F&A | Total Equipment only | Contingency equipment only
2.1 | 2nd beam test of SiPMS - finalize scintillator and SiPM choice | 2016-06-01 | 2016-06-30 | travel - requested separately |  |  |  | recent experience for 1 1-week + 1 2-week trips | BSF | 0 | 300 | recent experience for trip costs variations |  | 0
2.2 | Design frames for SiPM assembly & detectors, electronics readout cards | 2016-07-01 | 2016-11-01 | Labor | 8000 |  |  | outside designer, subcontract from TAU, estimate by RG |  | 8000 |  | Design uncertainty leads to larger contingency | 3200 | 8000
2.3 | Order BC422 (404?) from Saint-Gobain | 2016-07-01 | 2016-11-01 | Equipment | 4920 |  |  | Saint Gobain quote, 11/2/2015 | NSF / DOE | 4920 | 492 | 10% based on currency fluctuations | 738 | 5658 | 492
2.4 | Order Hamamatsu (Advancid) APDs | 2016-07-01 | 2016-11-01 | Equipment | 22262 |  |  | Hamamatsu quote to Alexey Stoykov | NSF / DOE | 22262 | 2226.2 | 10% based on inflation, discount | 3339.3 | 25601.3 | 2226.2
2.5 | Order amplifiers | 2016-07-01 | 2016-11-01 | Equipment | 15000 |  |  | from Alexey Stoykov | NSF / DOE | 15000 | 1500 | 10% based on inflation | 2250 | 17250 | 1500
2.5 | Order circuit boards | 2016-07-01 | 2016-11-01 | Equipment | 10730 |  |  | from Alexey Stoykov |  | 10730 | 2146 |  | 1609.5 | 12339.5 | 2146
2.6 | Build assembly frames | 2016-10-01 | 2016-11-01 | Equipment | 100 |  |  | from prototype fall 2015 | NSF / DOE | 100 | 20 | 10% based on inflation | 15 | 115 | 20
2.7 | Buy CFDs | 2016-10-01 | 2017-01-01 | Equipment | 70000 |  |  | PSI Electronics | NSF / DOE | 70000 | 7000 | 10% based on inflation, currency fluctuations |  | 70000 | 7000
2.8 | Build detector frames | 2016-10-01 | 2016-12-01 | Equipment | 1900 |  |  | from Alexey Stoykov | NSF / DOE | 1900 | 380 | 10% based on inflation | 285 | 2185 | 380
2.9 | Buy cables | 2016-11-01 | 2016-12-01 | Equipment | 2720 |  |  | from PSI catalog, 12/10/2015 | NSF / DOE | 2720 | 272 | 10% based on inflation |  | 2720 | 272
2.10 | Supplies | 2016-11-01 | 2016-11-30 | supplies - glue etc | 100 |  |  | glue for scintillator-APD bond, etc | NSF/DOE | 100 | 100 | Glues, tape, cable ties, … | 15 | 115 | 100
2.11 | cut and polish scintillator | 2016-11-01 | 2016-12-01 | Labor |  |  |  | Estimate based on prototype construction |  | 0
2.12 | assemble detector | 2016-12-01 | 2016-12-31 | Labor |  |  |  | Estimate based on prototype construction, frames assembled in parallel |  | 0
2.12.1 | wrap detectors | 2016-12-01 | 2016-12-31 | Labor |  |  |  | supplies for wrapping already in hand |  | 0 |  | tedlar or similar
2.13 | Detector cosmic tests | 2017-01-01 | 2017-03-31 | Labor |  |  |  | Characterize performance, perhaps borrowed equipment |  | 0 |  |  |  | 0 | 0
2.14 | Send detector to PSI | 2017-04-01 | 2017-05-01 | Shipping | 1000 |  |  | based on 12/2015 STT shipping, Israel to PSI, and same for return |  | 1000 | 200 | Might be assembled at PSI, only ship components | 280 |  | 200
2.15 | install SiPMs at PSI and commission | 2017-05-01 | 2017-06-01 | Travel - requested separately |  |  |  | recent experience for 2 2-week trips to Switzerland | BSF | 0 | 600 | recent experience for trip costs variations |  | 0
[13 empty] | 11731.8 | 143983.8 | 14336.2
| TOTAL |  |  |  | 136732 | 0 |  |  |  | 136732 | 14936.2 |  |  | 287967.6
| 1st yr TOTAL |  |  |  | 135732 | 0 |  |  |  | 135732 | 14136.2 |  |  | 143983.8
[5 empty] | 1000 | 0 |  |  |  | 1000 | 800 |  |  | 143983.8
|  | M&S | Status | Total
|  | Tubes | Firm
|  | Other stuff | Other
Labor
|  |  | Other | 4000
Notes
99.7 | assume no overhead from PSI
99.9 | assume no overhead from PSI
most others | 15% overhead from TAU
note: need to add Rutgers overheads!
| 1st year totals: can even $ flow by pushing CFDs + cables into year 2 | use few test | components | for first year
99.5,.6,.8 | Use 20% contingency, possible design changes