## Cerenkov - SiPM at target
WBS 3 | Beam Cerenkov part | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | F&A | Total Equipment only | Contingency equipment only
0
3.1 | beam test of Photek, Photonis | 2014-06-15 | 2015-12-31 | Travel | 0 |  |  | before this grant |  | 0 |  |  |  | 0
3.2 | Design Cerenkov frames and mounts | 2016-04-01 | 2016-09-01 | Labor | 0 |  |  | existing manpower |  | 0 |  |  |  | 0
3.3 | Order first 2 Photek MCP-PMT 240’s | 2016-06-01 | 2016-09-01 | Equipment | 45000 |  |  | Sydor quote, 11/2/2015 | NSF / DOE | 45000 | 4500 | 10% based on currency fluctuations |  | 45000 | 4500
3.4 | Build custom cables for BC readout | 2016-07-01 | 2016-09-01 | Equipment | 2400 |  |  | from cables built spring 2015 | NSF / DOE | 2400 | 240 | 10% based on inflation |  | 2400 | 240
3.5 | Order quartz radiators | 2016-07-01 | 2016-09-01 | Equipment | 800 |  |  | quartz from Technical Glass, recent purchases | NSF / DOE | 800 | 80 | 10% based on currency fluctuations | 224 | 1024 | 80
3.6 | Order mounting fixtures | 2016-09-01 | 2016-10-01 | Equipment | 100 |  |  | purchase of 3d printed mounting fixture in October 2013 | NSF/DOE | 100 | 2500 | contingency is for machined mounting fixtures |  | 100 | 2500
3.7 | Supplies | 2016-09-01 | 2016-10-01 | Labor | 0 |  |  | all existing, do not expect to need |  | 0 | 100 | In case electrical tape or optical grease or ... needed... |  | 0 | 100
3.8 | Construct frame for 1st prototype | 2016-09-01 | 2016-11-30 | parts & labor | 5500 | 4000 |  | Estimate based on crude design, to produce in Rutgers machine shop | NSF/DOE | 9500 | 2375 | Only crude design exists, not costed by machine shop | 2660 | 10160 | 2375
3.9 | Polish radiators | 2016-09-01 | 2016-11-01 | Labor | 0 |  |  | existing people, existing materials |  | 0 |  |  |  |  | 0
3.10 | Test of new MCPs at PSI | 2016-12-01 | 2016-12-20 | Travel - $3,500 |  |  |  | recent experience for 2-week trips to Switzerland | NSF/DOE | 0 | 300 | recent experience for trip costs variations |  | 0 | 0
3.11 | Data analysis | 2016-12-01 | 2017-02-01 | Labor | 0 |  |  | existing manpower | [5 empty] | 0 | 0
3.12 | Order 2 more Photek MCP-PMT 240’s | 2017-06-01 | 2017-09-01 | Equipment | 45000 |  |  | Sydor quote, 11/2/2015 | NSF/DOE | 45000 | 4500 |  |  | 45000 | 4500
3.13 | Order 4 ortec 9327 preamp/CFDs | 2017-06-01 | 2017-09-01 | Equipment | 12472 |  |  | Ametek quote, 11/2/2015 | NSF / DOE | 12472 | 1247.2 | 10% based on inflation, discount |  | 12472 | 1247.2
3.14 | Dress rehearsal run at PSI | 2017-11-01 | 2017-12-20 | Travel - $7,000 |  |  |  | recent experience for 2 2-week trips to Switzerland | NSF/DOE | 0 | 600 | recent experience for trip costs variations |  | 0 | 0
3.15 | Data analysis | 2017-11-01 | 2018-04-01 | Labor | 0 |  |  | existing manpower | [5 empty] | 0 | 0
3.16 | install Beam Cerenkov at PSI and commission | 2018-05-15 | 2018-06-01 | Travel - $7,000 |  |  |  | recent experience for 2 2-week trips to Switzerland | NSF/DOE | 0 | 600 | recent experience for trip costs variations |  | 0
[13 empty] | 2884 | 116156 | 15542.2
| TOTAL |  |  |  | 111272 | 4000 |  |  |  | 115272 | 17042.2 |  |  | 232312
| 1st yr TOTAL |  |  |  | 53800 | 4000 |  |  |  | 57800 | 10095 |  |  | 58684
[5 empty] | 57472 | 0 |  |  |  | 57472 | 6947.2 |  |  | 173628
|  | M&S | Status | Total
|  | Tubes | Firm | 90800
|  | Other stuff | Other | 5600
Labor
|  |  | Other | 4000
Notes
3.3 | never managed to test sapphire - | go with quartz
3.6 | now using ~$2500 rotary table
3.10 | Travel as part of this? or trigger? or?
3.14 | Travel as part of this? or trigger? or?
3.16 | Travel as part of this? or trigger? or?