## Sheet1
WBS 6 | Electronics & DAQ | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | Total
6.1 | Order first half of electronics | 2016-06-01 | 2016-12-01 | Labor & Equipment | 271991 |  |  | CAEN & GSI Quotes | NSF / DOE | 271991 | 30000 | EUR / USD exchange + loss of CAEN discount + possibly having to buy more expensive crates | 301991
6.2 | Organisation of mounting / power / infrastructure issues at PSI | 2016-03-01 | 2016-09-01 | Labor |  |  |  |  | NSF / DOE | 0 |  |  | 0
6.3 | Work on DAQ drivers & readout to improve speed | 2016-07-01 | 31-Jun-2016 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.4 | Receive delivery of electronics at PSI, and verify functionality | 2016-12-01 | 2017-03-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.5 | Mounting of electronics in "final" positions | 2017-02-01 | 2017-04-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.6 | Planning, prototyping and ordering cable components | 2017-04-01 | 2017-06-01 | L & E | 50000 |  | 0 | Estimates based on catalogue parts costs | NSF/DOE | 50000 | 10000 | Changing connector requirements / exchange rate estimates / possible delay cable requirements | 60000
6.7 | Cable manufacture, testing & installation, mounting on table where appropriate | 2017-06-01 | 2017-09-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.8 | Installation of DAQ software & integration of complete DAQ to read out all components. | 2017-08-01 | 2017-10-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.10 | Update quotes & place order for RAID array and any residual electronics needs | 2017-06-01 | 2017-08-01 | Labor | 88291 |  |  | DELL Quote | NSF/DOE | 88291 | 10595 | 10% fluctuation due to price change / increased storage need | 98886
6.11 | Receive delivery of remaining electronics & RAID Array at PSI, and verify functionality | 2017-12-01 | 2018-03-01 | Labor & Equipment |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.12 | Install electronics in final position and complete cabling | 2018-03-01 | 2018-04-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.13 | Install software and complete integration of new DAQ components | 2018-04-01 | 2018-05-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.14 | Final testing & improvement of DAQ software | 2018-05-01 | 2018-07-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
[10 empty] | 410282 | 50595 |  | 460877
Labor
[9 empty] | Salaries | 213312
[9 empty] | Pdfringe | 32246.472
[9 empty] | GS fringe | 4726.8
[9 empty] | UG fringe | 7878
[9 empty] | Total | 258163.272
[9 empty] | F & A | 135535.7178
[9 empty] | Toatal with F & A | 393698.9898
[9 empty] | Contingency | 25816.3272
[9 empty] | Total contingency | 76411.3272
[13 empty] | #DIV/0! | Percent Contingency