## SiPM
WBS 99 | Beam Monitor part | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Employee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | F&A | Total Equipment only | Contingency equipment only
99.1 | Beam test of Beam Monitor detector | 2016-06-01 | 2016-06-30 | travel - requested separately |  |  |  | recent experience for 1 1-week + 1 2-week trips | BSF | 0 | 300 | recent experience for trip costs variations |  | 0
99.2 | Design frames for SiPM assembly & detectors, electronics readout cards | 2016-07-01 | 2016-11-01 | Labor | 2000 |  |  | outside designer, subcontract from TAU, estimate by RG |  | 2000 |  | Design uncertainty leads to larger contingency | 800 | 2000
99.3 | Order 3 mm wide BC404 from Saint-Gobain | 2016-07-01 | 2016-11-01 | Equipment | 4920 |  |  | Ask for a quotation from Saint Gobain | NSF / DOE | 4920 | 492 | 10% based on currency fluctuations | 738 | 5658 | 492
99.4 | Order 200 AdvanSid APDs | 2016-07-01 | 2016-11-01 | Equipment | 4570 |  |  | AdvanSiD quote | NSF / DOE | 4570 | 457 | 10% based on inflation, discount | 685.5 | 5255.5 | 457
99.5 | Order 50 amplifiers | 2016-07-01 | 2016-11-01 | Equipment | 3750 |  |  | from Alexey Stoykov | NSF / DOE | 3750 | 375 | 10% based on inflation | 562.5 | 4312.5 | 375
99.5 | Order 50 circuit boards | 2016-07-01 | 2016-11-01 | Equipment | 2680 |  |  | from Alexey Stoykov |  | 2680 | 536 |  | 402 | 3082 | 536
99.6 | Build assembly frames | 2016-10-01 | 2016-11-01 | Equipment | 100 |  |  | from prototype fall 2015 | NSF / DOE | 100 | 20 | 10% based on inflation | 15 | 115 | 20
99.7 | Buy 50 CFDs | 2016-10-01 | 2017-01-01 | Equipment | 17500 |  |  | PSI Electronics | NSF / DOE | 17500 | 1750 | 10% based on inflation, currency fluctuations |  | 17500 | 1750
99.8 | Build detector frames | 2016-10-01 | 2016-12-01 | Equipment | 1900 |  |  | PSI | NSF / DOE | 1900 | 380 | 10% based on inflation | 285 | 2185 | 380
99.9 | Buy cables | 2016-11-01 | 2016-12-01 | Equipment | 680 |  |  | from PSI catalog, 12/10/2015 | NSF / DOE | 680 | 68 | 10% based on inflation |  | 680 | 68
99.10 | Supplies | 2016-11-01 | 2016-11-30 | supplies - glue etc | 500 |  |  | glue for scintillator-APD bond, etc | NSF/DOE | 500 | 100 | Glues, tape, cable ties, … | 75 | 575 | 100
99.11 | cut and polish scintillator | 2016-11-01 | 2016-12-01 | Labor |  |  |  | Estimate based on prototype construction |  | 0
99.12 | assemble detector | 2016-12-01 | 2016-12-31 | Labor |  |  |  | Estimate based on prototype construction, frames assembled in parallel |  | 0
99.12.1 | wrap detectors | 2016-12-01 | 2016-12-31 | Labor |  |  |  | supplies for wrapping already in hand |  | 0 |  | tedlar or similar
99.13 | Detector cosmic tests | 2017-01-01 | 2017-03-31 | Labor |  |  |  | Characterize performance, perhaps borrowed equipment |  | 0 |  |  |  | 0 | 0
99.14 | install the beam-monitor at PSI and commission | 2017-05-01 | 2017-06-01 | Travel - requested separately |  |  |  | recent experience for 2 2-week trips to Switzerland | BSF | 0 | 600 | recent experience for trip costs variations |  | 0
[13 empty] | 3563 | 41363 | 4178
| TOTAL |  |  |  | 38600 | 0 |  |  |  | 38600 | 4778 |  |  | 82726
| 1st yr TOTAL |  |  |  | 38600 | 0 |  |  |  | 38600 | 4178 |  |  | 41363
[5 empty] | 0 | 0 |  |  |  | 0 | 600 |  |  | 41363
|  | M&S | Status | Total
|  | Tubes | Firm
|  | Other stuff | Other
Labor
|  |  | Other | 4000
Notes
99.7 | assume no overhead from PSI
99.9 | assume no overhead from PSI
most others | 15% overhead from TAU
note: need to add Rutgers overheads!
| 1st year totals: can even $ flow by pushing CFDs + cables into year 2 | use few test | components | for first year
99.5,.6,.8 | Use 20% contingency, possible design changes