## MUSE-cost-summary.txt
WBS-Code | Title | M&S | Labor | F&A | Contingency | Total w/o Contingency | Total with Contingency | BOE | Notes
4 | Straw Chambers | [6 empty] | Quotes, PANDA experience
4.1 | Order straw material | 351417 |  | 0 | 146307 | 351417 | 497724
4.2 | Order gas system | 17550 |  | 0 | 4738 | 17550 | 22288
4.3 | Set up clean room | 15000 | 5000 | 1250 | 2550 | 21250 | 23800
4.4 | Manufacture Jigs | 1000 |  | 0 | 120 | 1000 | 1120
4.5 | Design/build chamber mounting | 3000 | 5000 | 1250 | 1110 | 9250 | 10360
4.6 | manufacture straws ch 1 |  |  | 0 | 0 | 0 | 0
4.7 | manufacture gas dist. |  |  | 0 | 0 | 0 | 0
4.8 | machine chamber mounting |  | 5000 | 1250 | 750 | 6250 | 7000 |  | Machine shop
4.9 | assemble & test ch 1 |  |  | 0 | 0 | 0 | 0
4.1 | ship to PSI |  | 2000 | 500 | 300 | 2500 | 2800
4.11 | Commission ch 1 at PSI |  |  | 0 | 0 | 0 | 0
4.12 | Ch 1 ready at PSI |  |  | 0 | 0 | 0 | 0
4.13 | Purchase remaing gas system | 26325 |  | 0 | 7107 | 26325 | 33432
4.14 | Build ch 2-4 |  |  | 0 | 0 | 0 | 0
4.15 | Ship ch 2-4 to psi |  | 4000 | 1000 | 600 | 5000 | 5600
4.16 | Commision at PSI |  |  | 0 | 0 | 0 | 0
| Labor |  | 140436 | 35032 | 35093.6 | 175468 | 210561.6
| Total | 414292 | 161436 | 40282 | 198675.6 | 616010 | 814685.6
| Labor summary | Tech | HU GS |  | Temple GS | Travel Temple GS for construction
|  | 0 | 60000 | Stipend | 43026 | 25200
|  | 1 FTE | 2 FTE | Fringe+ tuition | 12210
|  | 1/2 for 2 years | 1 student, 2 years |  | 9 month year 1, 12 month year 2
|  | F&A | 15000 | F&A | 13480 | 6552
31752