## Sheet1 - Table 1
WBS 1 | Frames | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | Total
(machine shop charges)
1.1 | Design table | 2013-12-01 | 2015-03-01 | Labor |  |  |  | existing manpower | NSF/DOE
1.2 | Buy table rotary bearings | 2015-03-01 | 2015-04-01 | parts | 3355.33 |  |  | quote from BWC.com to Argonne, 1/16/2014 | NSF/DOE | 3355.33 | 167.7665 | inflation, shipping | 3523.0965
1.3 | Buy extrusions for frame | 2015-03-01 | 2015-04-01 | parts | 4000 |  |  | estimate from Paul Reimer | NSF/DOE | 4000 | 200 | inflation, shipping | 4200
1.4 | machine donuts and table | 2015-03-01 | 2015-04-01 | parts | 7000 |  |  | estimate from Paul Reimer | NSF/DOE | 7000 | 700 | not estimated by shop | 7700
1.5 | Buy table linear bearings | 2015-03-01 | 2015-04-01 | parts | 2100 |  |  | Thomson rails | NSF/DOE | 2100 | 315 | rough guess. Note opportunity: might have pre-existing rails. | 2415
1.6 | Machine extrusions and assemble table | 2015-04-01 | 2015-05-01 | labor |  | 4800 |  | physicist estimate from crude initial drawings | NSF / DOE | 4800 | 1440 | not estimated by shop | 6240
1.8 | Ship table to PSI | 2015-05-01 | 2015-06-01 | shipping | 8000 |  |  | hand waving | NSF / DOE | 8000 | 4000 | rough guess... | 12000
1.9 | Assemble table at PSI | 2015-06-01 | 2015-07-01
1.10 | Design scintillator wall frames | 2014-07-01 | 2015-03-01 | Labor |  |  |  | existing manpower | NSF / DOE
1.11 | Construct 1st scintillator wall frame | 2015-03-01 | 2015-05-01 | parts & labor | 1500 | 1500 |  | physicist estimate from crude ideas, no drawings yet | NSF/DOE | 3000 | 1500 | extremely crude design, no designer work to date | 4500
1.12 | Ship 1st wall frames to PSI, with table above | 2015-05-01 | 2015-06-01
1.13 | Assemble 1st scintillator wall frame at PSI | 2015-06-01 | 2015-07-01
1.14 | Design frame for veto mount to scattering chamber | 2015-06-01 | 2015-08-01 | Labor |  |  |  | existing manpower | NSF/DOE | 0 | 0 |  | 0
1.15 | Build veto frame | 2015-08-01 | 2015-09-01 | parts & labor | 250 | 250 |  | physicist estimate from crude ideas, no drawings yet | NSF/DOE | 500 | 250 | extremely crude design, no designer work to date | 750
1.16 | bring veto frame to PSI | 2015-09-01 | 2015-10-01 |  | 0 |  |  | (carry on item?)
1.17 | Design frame for beam monitor | 2015-06-01 | 2015-08-01 | Labor | 0 |  |  | existing manpower | NSF/DOE | 0 | 0 |  | 0
1.18 | Construct beam monitor frame | 2015-08-01 | 2015-09-01 | parts & labor | 500 | 500 |  | physicist estimate from crude ideas, no drawings yet | NSF/DOE | 1000 | 500 | extremely crude design, no designer work to date | 1500
1.19 | Ship beam monitor frame to PSI | 2015-09-01 | 2015-10-01
1.20 | Assemble beam monitor frame at PSI | 2015-10-01 | 2015-11-01
1.21 | Construct 2nd scintillator wall frame | 2016-01-01 | 2016-03-01 | parts & labor | 1500 | 1500 |  | physicist estimate from crude ideas, no drawings yet | NSF/DOE | 3000 | 1500 | extremely crude design, no designer work to date | 4500
1.22 | Ship 2nd wall frames to PSI, with table above | 2016-03-01 | 2016-04-01 |  | 2000 |  |  |  |  | 2000
1.23 | Assemble 2nd scintillator wall frame at PSI | 2016-04-01 | 2016-05-01
1.24 | ship frames home at end of experiment | 2018-02-01 | 2018-03-01 | shipping | 10000 |  |  | hand waving | NSF / DOE | 10000 | 5000 | rough guess... | 15000
| TOTAL: |  |  |  | 40205.33 | 8550 |  |  |  | 48755.33 | 15572.7665 |  | 62328.0965
| TOTAL Yr 1 |  |  |  | 25955.33 | 6300 |  |  |  | 32255.33 | 8322.7665 |  | 40578.0965
| TOTAL YR 2 |  |  |  | 14250 | 2250 |  |  |  | 16500 | 7250 |  | 21750
NOTES:
Beam Cerenkov and SciFi frames under those projects
Does not include overheads on this sheet
[9 empty] | Total W/O Contingency | 97510.66
[9 empty] | Total with Travel W/O Contingency | 97510.66 | 97510.66 |  | 0
-100%