## Sheet1
SciFi | start date | end date | M&S or Labor | Cost | BOE
Sent out orders for SciFi, WLS Fibers, PMTs | 2014-07-31 | 2015-01-27 | M&S | 68100 | Quotes
Design mounting structures | 2014-07-31 | 2014-09-29 | Labor |  | Estimate
Order cutting/polishing tools | 2014-07-31 | 2014-09-29 | M&S | 15000 | Quotes | From non NSF/DOE Sources
Design Bases + Electronics | 2014-07-31 | 2014-09-29 | Both |  | E-Shop
Prototype construction | 2015-02-01 | 2015-03-03 | Labor
Construct fibers | 2015-03-01 | 2015-05-30 | Labor
Machine frames | 2015-04-01 | 2015-05-01 | Labor
Mount Fibers | 2015-06-01 | 2015-07-01 | Labor
Commisioning tests at TAU | 2015-07-01 | 2015-07-31 | Labor
Shipping to PSI | 2015-08-01 | 2015-08-31 | Labor
Tests at PSI (Beam + Cosmics) | 2015-09-01 | 2015-10-31 | Labor
Formulas:
end date = [start date]+180