## Sheet1
Straw Chambers | start date | end date | M&S or Labor | Cost | BOE | split
[6 empty] | M&S | Labor
Send out orders for straws, wire, connector pins, gas manifolds, ABS endcaps | 2014-07-31 | 2015-01-27 | M&S | 200424 | Quotes + Estimates from PANDA | 200424
Purchase one gas system | 2014-09-01 | 2014-10-31 | M&S | 12150 | Quotes | 12150
Finalize Clean Fab Environment | 2014-07-31 | 2014-09-29 | Both | 20000 | Estimate | 15000 | 5000
Manufacture Construction Jigs | 2014-07-31 | 2014-09-29 | Both | 5000 | Estimate | 1000 | 4000
Design PCBs for Readout and HV | 2014-07-31 | 2014-09-29 | Labor | 0 | E-Shop
Purchase PCB components and manufacture bords | 2014-10-01 | 2014-11-30 | Both | 10000 | E-Shop + Students | 5000 | 5000
Design Chamber Mounting | 2014-09-30 | 2014-11-29 | Labor | 5000 | Estimate from similar projects (Designer) |  | 5000
Manufature Straws | 2015-02-01 | 2016-02-01 | Labor |  | Students+Tech
Manufacture Gas Distirubtion Setup (including control software) | 2015-02-01 | 2015-04-02 | Labor |  | Students + Machine Shop
Machining of Chamber Mountings | 2014-12-01 | 2015-01-30 | Labor | 5000 | Machine Shop |  | 5000
Mount and test chamber 1 | 2015-04-01 | 2015-05-31 | Labor |  | Students+Tech
Ship Chamber 1 to PSI | 2015-06-01 | 2015-07-01 | Both | 2000 | Estimate | 1500 | 500
Commision Chamber 1 at PSI | 2015-07-01 | 2015-07-31 |  |  | Studens
Purchase remaining gas system | 2015-03-01 | 2015-04-30 | M&S | 23850 | Quotes | 23850
Mount and Test Chambers 2-4 | 2015-06-01 | 2016-04-01 | Labor |  | Students+Tech
Ship Chambers to PSI | 2016-04-01 | 2016-05-01 | Both | 4000 |  | 3000 | 1000
Commision Chambers 2-4 at PSI | 2016-05-01 | 2016-05-31 | Labor |  | Studens
[6 empty] | 261924 | 25500
|  | 180000 | 45000 | 225000
|  | 65661 |  | 45000
|  | 11600 |  | 180000
|  | 257261 |  | 25500
205500
Formulas:
end date = [start date]+180