## MUSE-gannt-feb13-2014.txt
Nr | Info | WBS-Code | Title | Given Planned Duration | ID | Flag Status | Nr Predecessors | Actual Start | Expected Duration | Expected Start | Expected End | Milestone | Assigned Resources | Percent Complete | Assignment
1 |  | 1 | Frames & Design |  | 7 | None |  |  | 1.87 years | 2014-03-01 08:00 | 2015-11-18 17:00 | 0 |  | 0% | 0
2 |  | 1.1 | Table |  | 36 | Auto |  |  | 1.12 years | 2014-03-01 08:00 | 2015-03-13 17:00 | 0 |  | 0% | 0
3 |  | 1.1.1 | Design table | 9 months | 47 | Auto |  | 2014-03-01 08:00 | 9 months | 2014-03-01 08:00 | 2014-11-07 17:00 | 0 |  | 0% | 0
4 |  | 1.1.2 | Buy table parts |  | 125 | Auto | 3; 130 |  | 1 month | 2014-11-10 08:00 | 2014-12-05 17:00 | 0 |  | 0% | 0
5 |  | 1.1.2.1 | rotary bearings | 1 month | 92 | Auto |  |  | 1 month | 2014-11-10 08:00 | 2014-12-05 17:00 | 0 |  | 0% | 0
6 |  | 1.1.2.2 | extrutions for frame | 1 month | 4 | Auto |  |  | 1 month | 2014-11-10 08:00 | 2014-12-05 17:00 | 0 |  | 0% | 0
7 |  | 1.1.2.3 | linear bearings | 1 month | 67 | Auto |  |  | 1 month | 2014-11-10 08:00 | 2014-12-05 17:00 | 0 |  | 0% | 0
8 |  | 1.1.3 | Machine & assemble table |  | 74 | Auto | 4 |  | 1.5 months | 2014-12-08 08:00 | 2015-01-16 17:00 | 0 |  | 0% | 0
9 |  | 1.1.3.1 | machine donuts and table | 1 month | 30 | Auto |  |  | 1 month | 2014-12-08 08:00 | 2015-01-02 17:00 | 0 |  | 0% | 0
10 |  | 1.1.3.2 | machine extrusions | 1 month | 98 | Auto |  |  | 1 month | 2014-12-08 08:00 | 2015-01-02 17:00 | 0 |  | 0% | 0
11 |  | 1.1.3.3 | assemble table | 2 weeks | 91 | Auto | 9; 10 |  | 2 weeks | 2015-01-05 08:00 | 2015-01-16 17:00 | 0 |  | 0% | 0
12 |  | 1.1.4 | Ship and assemble table |  | 60 | Auto |  |  | 2 months | 2015-01-19 08:00 | 2015-03-13 17:00 | 0 |  | 0% | 0
13 |  | 1.1.4.1 | Ship to PSI | 1 month | 113 | Auto | 8 |  | 1 month | 2015-01-19 08:00 | 2015-02-13 17:00 | 0 |  | 0% | 0
14 |  | 1.1.4.2 | Assemble table at PSI | 1 month | 1 | Auto | 13 |  | 1 month | 2015-02-16 08:00 | 2015-03-13 17:00 | 0 |  | 0% | 0
15 |  | 1.2 | Table ready at PSI |  | 86 | Auto | 14 |  | 0 hours | 2015-03-13 17:00 | 2015-03-13 17:00 | 1 |  | 0% | 0
16 |  | 1.3 | Scintillator and Veto |  | 48 | Auto |  |  | 1.42 years | 2014-07-01 08:00 | 2015-10-21 17:00 | 0 |  | 0% | 0
17 |  | 1.3.1 | Design scintillator frames | 6 months | 96 | Auto |  | 2014-07-01 08:00 | 6 months | 2014-07-01 08:00 | 2014-12-15 17:00 | 0 |  | 0% | 0
18 |  | 1.3.2 | Build first scintillator frame | 2 months | 66 | Auto | 17; 130 |  | 2 months | 2014-12-16 08:00 | 2015-02-09 17:00 | 0 |  | 0% | 0
19 |  | 1.3.3 | Ship first frames to PSI | 1 month | 54 | Auto | 18 |  | 1 month | 2015-02-10 08:00 | 2015-03-09 17:00 | 0 |  | 0% | 0
20 |  | 1.3.4 | Build second scint. frames | 2 months | 38 | Auto | 18; 131 |  | 2 months | 2015-07-02 08:00 | 2015-08-26 17:00 | 0 |  | 0% | 0
21 |  | 1.3.5 | Ship second set to PSI | 1 month | 120 | Auto | 20 |  | 1 month | 2015-08-27 08:00 | 2015-09-23 17:00 | 0 |  | 0% | 0
22 |  | 1.3.6 | Assemble at PSI | 1 month | 80 | Auto | 21 |  | 1 month | 2015-09-24 08:00 | 2015-10-21 17:00 | 0 |  | 0% | 0
23 |  | 1.3.7 | Veto design | 2 months | 8 | Auto | 17 |  | 2 months | 2014-12-16 08:00 | 2015-02-09 17:00 | 0 |  | 0% | 0
24 |  | 1.3.8 | Build veto | 1 month | 103 | Auto | 23 |  | 1 month | 2015-02-10 08:00 | 2015-03-09 17:00 | 0 |  | 0% | 0
25 |  | 1.3.9 | Ship veto to PSI | 1 month | 14 | Auto | 24 |  | 1 month | 2015-03-10 08:00 | 2015-04-06 17:00 | 0 |  | 0% | 0
26 |  | 1.4 | Beam Monitor |  | 68 | Auto |  |  | 5 months | 2015-07-02 08:00 | 2015-11-18 17:00 | 0 |  | 0% | 0
27 |  | 1.4.1 | Design beam monitor | 2 months | 61 | Auto | 23; 131 |  | 2 months | 2015-07-02 08:00 | 2015-08-26 17:00 | 0 |  | 0% | 0
28 |  | 1.4.2 | Build beam monitor | 1 month | 15 | Auto | 27 |  | 1 month | 2015-08-27 08:00 | 2015-09-23 17:00 | 0 |  | 0% | 0
29 |  | 1.4.3 | Ship to PSI | 1 month | 122 | Auto | 28 |  | 1 month | 2015-09-24 08:00 | 2015-10-21 17:00 | 0 |  | 0% | 0
30 |  | 1.4.4 | Assemble PSI | 1 month | 42 | Auto | 29 |  | 1 month | 2015-10-22 08:00 | 2015-11-18 17:00 | 0 |  | 0% | 0
31 |  | 2 | Scintillating Fiber |  | 40 | Auto |  |  | 1.21 years | 2014-07-02 08:00 | 2015-08-11 17:00 | 0 |  | 0% | 0
32 |  | 2.1 | Order Materials |  | 99 | Auto | 130 |  | 6 months | 2014-07-02 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
33 |  | 2.1.1 | Order Fiber | 6 months | 64 | Auto |  |  | 6 months | 2014-07-02 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
34 |  | 2.1.2 | Order PMTs | 6 months | 53 | Auto |  |  | 6 months | 2014-07-02 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
35 |  | 2.1.3 | Order tools | 2 months | 107 | Auto |  |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
36 |  | 2.2 | Prototype | 1 month | 112 | Auto | 32 |  | 1 month | 2014-12-17 08:00 | 2015-01-13 17:00 | 0 |  | 0% | 0
37 |  | 2.3 | Construct fibers | 3 months | 16 | Auto | 36 |  | 3 months | 2015-01-14 08:00 | 2015-04-07 17:00 | 0 |  | 0% | 0
38 |  | 2.4 | Mount fibers | 1 month | 43 | Auto | 37 |  | 1 month | 2015-04-08 08:00 | 2015-05-05 17:00 | 0 |  | 0% | 0
39 |  | 2.5 | Testing | 1 month | 76 | Auto | 38 |  | 1 month | 2015-05-06 08:00 | 2015-06-02 17:00 | 0 |  | 0% | 0
40 |  | 2.6 | Ship to PSI | 2 weeks | 20 | Auto | 39 |  | 2 weeks | 2015-06-03 08:00 | 2015-06-16 17:00 | 0 |  | 0% | 0
41 |  | 2.7 | Test at PSI | 2 months | 59 | Auto | 40 |  | 2 months | 2015-06-17 08:00 | 2015-08-11 17:00 | 0 |  | 0% | 0
42 |  | 3 | Cerenkov |  | 105 | None |  |  | 1.87 years | 2014-02-03 08:00 | 2015-10-21 17:00 | 0 |  | 0% | 0
43 |  | 3.1 | Design Cerenkov | 5 months | 85 | None |  |  | 5 months | 2014-02-03 08:00 | 2014-06-20 17:00 | 0 |  | 0% | 0
44 |  | 3.2 | Buy materials first part |  | 77 | Auto | 130 |  | 4 months | 2014-07-02 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
45 |  | 3.2.1 | Buy first 4 tubes | 4 months | 109 | None |  |  | 4 months | 2014-07-02 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
46 |  | 3.2.2 | Buy sapphire | 3 months | 73 | None |  |  | 3 months | 2014-07-02 08:00 | 2014-09-23 17:00 | 0 |  | 0% | 0
47 |  | 3.2.3 | Buy assembly materials | 1 month | 45 | Auto |  |  | 1 month | 2014-07-02 08:00 | 2014-07-29 17:00 | 0 |  | 0% | 0
48 |  | 3.3 | Assemble | 2 months | 33 | Auto | 44 |  | 2 months | 2014-10-22 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
49 |  | 3.4 | Ship to PSI | 1 month | 13 | Auto | 48 |  | 1 month | 2014-12-17 08:00 | 2015-01-13 17:00 | 0 |  | 0% | 0
50 |  | 3.5 | First set at PSI |  | 51 | None | 49 |  | 0 hours | 2015-01-13 17:00 | 2015-01-13 17:00 | 1 |  | 0% | 0
51 |  | 3.6 | Buy 5 tubes | 4 months | 9 | Auto | 131 |  | 4 months | 2015-07-02 08:00 | 2015-10-21 17:00 | 0 |  | 0% | 0
52 |  | 3.7 | Buy mounting fixtures | 1 month | 34 | Auto | 131 |  | 1 month | 2015-07-02 08:00 | 2015-07-29 17:00 | 0 |  | 0% | 0
53 |  | 3.8 | Frame for 2nd cerenkov | 2 months | 71 | Auto | 52 |  | 2 months | 2015-07-30 08:00 | 2015-09-23 17:00 | 0 |  | 0% | 0
54 |  | 3.9 | Install at PSI | 1 month | 90 | Auto | 53 |  | 1 month | 2015-09-24 08:00 | 2015-10-21 17:00 | 0 |  | 0% | 0
55 |  | 4 | Straw Chambers |  | 87 | Auto | 130 |  | 1.83 years | 2014-07-02 08:00 | 2016-03-08 17:00 | 0 |  | 0% | 0
56 |  | 4.1 | Order straw material | 6 months | 11 | Auto |  |  | 6 months | 2014-07-02 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
57 |  | 4.2 | Order gas system | 2 months | 118 | Auto |  |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
58 |  | 4.3 | Set up clean room | 2 months | 57 | Auto | 130 |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
59 |  | 4.4 | Manufacture Jigs | 2 months | 111 | Auto | 130 |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
60 |  | 4.5 | Design chamber mounting | 2 months | 127 | Auto | 130 |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
61 |  | 4.6 | manufacture straws ch 1 | 2 months | 75 | Auto | 56; 58; 59 |  | 2 months | 2014-12-17 08:00 | 2015-02-10 17:00 | 0 |  | 0% | 0
62 |  | 4.7 | manufacture gas dist. | 2 months | 95 | Auto | 57 |  | 2 months | 2014-08-27 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
63 |  | 4.8 | machine chamber mounting | 2 months | 6 | Auto | 60 |  | 2 months | 2014-08-27 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
64 |  | 4.9 | assemble & test ch 1 | 2 months | 65 | Auto | 61; 63 |  | 2 months | 2015-02-11 08:00 | 2015-04-07 17:00 | 0 |  | 0% | 0
65 |  | 4.1 | ship to PSI | 1 month | 69 | Auto | 64 |  | 1 month | 2015-04-08 08:00 | 2015-05-05 17:00 | 0 |  | 0% | 0
66 |  | 4.11 | Commission ch 1 at PSI | 1 month | 97 | Auto | 65 |  | 1 month | 2015-05-06 08:00 | 2015-06-02 17:00 | 0 |  | 0% | 0
67 |  | 4.12 | Ch 1 ready at PSI |  | 19 | Auto | 66 |  | 0 hours | 2015-06-02 17:00 | 2015-06-02 17:00 | 1 |  | 0% | 0
68 |  | 4.13 | Purchase 2nd gas system | 1 month | 21 | Auto | 61 |  | 1 month | 2015-02-11 08:00 | 2015-03-10 17:00 | 0 |  | 0% | 0
69 |  | 4.14 | Build ch 2-4 | 9 months | 119 | Auto | 64 |  | 9 months | 2015-04-08 08:00 | 2015-12-15 17:00 | 0 |  | 0% | 0
70 |  | 4.15 | Ship ch 2-4 to psi | 1 month | 2 | Auto | 69 |  | 1 month | 2015-12-16 08:00 | 2016-01-12 17:00 | 0 |  | 0% | 0
71 |  | 4.16 | Commision at PSI | 2 months | 79 | Auto | 70 |  | 2 months | 2016-01-13 08:00 | 2016-03-08 17:00 | 0 |  | 0% | 0
72 |  | 5 | Cryo-target |  | 37 | Auto |  |  | 2.28 years | 2014-03-01 08:00 | 2016-04-05 17:00 | 0 |  | 0% | 0
73 |  | 5.1 | Set up lab | 3 months | 28 | Auto |  | 2014-03-01 08:00 | 3 months | 2014-03-01 08:00 | 2014-05-23 17:00 | 0 |  | 0% | 0
74 |  | 5.2 | Do Design | 4 months | 55 | Auto |  | 2014-03-01 08:00 | 4 months | 2014-03-01 08:00 | 2014-06-20 17:00 | 0 |  | 0% | 0
75 |  | 5.3 | Order major elements | 2 months | 25 | Auto | 74; 130 |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
76 |  | 5.4 | Construct prototype | 2 months | 56 | Auto | 75 |  | 2 months | 2014-08-27 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
77 |  | 5.5 | Test and eval. of prototype | 2 months | 5 | Auto | 76 |  | 2 months | 2014-10-22 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
78 |  | 5.6 | Redesign and 2nd proto. | 2 months | 115 | Auto | 77 |  | 2 months | 2014-12-17 08:00 | 2015-02-10 17:00 | 0 |  | 0% | 0
79 |  | 5.7 | Test and final design | 2 months | 46 | Auto | 78 |  | 2 months | 2015-02-11 08:00 | 2015-04-07 17:00 | 0 |  | 0% | 0
80 |  | 5.8 | Target Cell design |  | 23 | Auto | 79 |  | 0 hours | 2015-04-07 17:00 | 2015-04-07 17:00 | 1 |  | 0% | 0
81 |  | 5.9 | Const. Scatt. Chamb. & cells | 2 months | 82 | Auto | 79 |  | 2 months | 2015-04-08 08:00 | 2015-06-02 17:00 | 0 |  | 0% | 0
82 |  | 5.1 | Test and Evaluate | 3 months | 29 | Auto | 81 |  | 3 months | 2015-06-03 08:00 | 2015-08-25 17:00 | 0 |  | 0% | 0
83 |  | 5.11 | Test complete system | 2 months | 10 | Auto | 82 |  | 2 months | 2015-08-26 08:00 | 2015-10-20 17:00 | 0 |  | 0% | 0
84 |  | 5.12 | Review | 1 month | 72 | Auto | 83 |  | 1 month | 2015-10-21 08:00 | 2015-11-17 17:00 | 0 |  | 0% | 0
85 |  | 5.13 | Ship and set up | 2 months | 93 | Auto | 84 |  | 2 months | 2015-11-18 08:00 | 2016-01-12 17:00 | 0 |  | 0% | 0
86 |  | 5.14 | In situ testing | 1 month | 108 | Auto | 85 |  | 1 month | 2016-01-13 08:00 | 2016-02-09 17:00 | 0 |  | 0% | 0
87 |  | 5.15 | Final review | 2 months | 24 | Auto | 86 |  | 2 months | 2016-02-10 08:00 | 2016-04-05 17:00 | 0 |  | 0% | 0
88 |  | 5.16 | Ready to Run |  | 117 | Auto | 87 |  | 0 hours | 2016-04-05 17:00 | 2016-04-05 17:00 | 1 |  | 0% | 0
89 |  | 6 | Electronics & DAQ |  | 17 | None |  |  | 2.17 years | 2014-07-02 08:00 | 2016-06-28 17:00 | 0 |  | 0% | 0
90 |  | 6.1 | Order first half electronics | 6 months | 52 | None | 130 |  | 6 months | 2014-07-02 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
91 |  | 6.2 | Mounting/order cables | 2 months | 114 | Auto | 90 |  | 2 months | 2014-12-17 08:00 | 2015-02-10 17:00 | 0 |  | 0% | 0
92 |  | 6.3 | Manufacture/Install cables | 2 months | 44 | Auto | 91 |  | 2 months | 2015-02-11 08:00 | 2015-04-07 17:00 | 0 |  | 0% | 0
93 |  | 6.4 | Develop DAQ | 1 year | 130 | Auto | 130 |  | 1 year | 2014-07-02 08:00 | 2015-06-02 17:00 | 0 |  | 0% | 0
94 |  | 6.5 | Install and test complete DAQ | 2 months | 62 | Auto | 92; 93 |  | 2 months | 2015-06-03 08:00 | 2015-07-28 17:00 | 0 |  | 0% | 0
95 |  | 6.6 | DAQ ready for test run |  | 129 | Auto | 94 |  | 0 hours | 2015-07-28 17:00 | 2015-07-28 17:00 | 1 |  | 0% | 0
96 |  | 6.7 | Order 2nd half electronics | 6 months | 102 | Auto | 131 |  | 6 months | 2015-07-02 08:00 | 2015-12-16 17:00 | 0 |  | 0% | 0
97 |  | 6.8 | Optimize DAQ | 1 year | 131 | Auto | 94 |  | 1 year | 2015-07-29 08:00 | 2016-06-28 17:00 | 0 |  | 0% | 0
98 |  | 6.9 | Install and complete DAQ | 3 months | 12 | Auto | 96 |  | 3 months | 2015-12-17 08:00 | 2016-03-09 17:00 | 0 |  | 0% | 0
99 |  | 6.1 | Final test of DAQ | 3 months | 58 | Auto | 98 |  | 3 months | 2016-03-10 08:00 | 2016-06-01 17:00 | 0 |  | 0% | 0
100 |  | 6.11 | Write initial analysis program | 1 year | 132 | Auto | 130 |  | 1 year | 2014-07-02 08:00 | 2015-06-02 17:00 | 0 |  | 0% | 0
101 |  | 7 | Scintillators |  | 31 | Auto | 130 |  | 6.5 months | 2014-07-02 08:00 | 2014-12-30 17:00 | 0 |  | 0% | 0
102 |  | 7.1 | Scintillator Purchase |  | 18 | Auto |  |  | 4 months | 2014-07-02 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
103 |  | 7.1.1 | Order first half | 2 months | 39 | Auto |  |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
104 |  | 7.1.2 | Order second half | 2 months | 81 | Auto | 103 |  | 2 months | 2014-08-27 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
105 |  | 7.1.3 | Order PMTs | 40 days | 3 | Auto |  |  | 2 months | 2014-07-02 08:00 | 2014-08-26 17:00 | 0 |  | 0% | 0
106 |  | 7.1.4 | Supplies | 2 weeks | 123 | Auto |  |  | 2 weeks | 2014-07-02 08:00 | 2014-07-15 17:00 | 0 |  | 0% | 0
107 |  | 7.2 | Scintillator Construction |  | 110 | Auto |  |  | 4.5 months | 2014-08-27 08:00 | 2014-12-30 17:00 | 0 |  | 0% | 0
108 |  | 7.2.1 | Wrap first half | 2 months | 26 | Auto | 103; 106 |  | 2 months | 2014-08-27 08:00 | 2014-10-21 17:00 | 0 |  | 0% | 0
109 |  | 7.2.2 | Wrap second half | 2 months | 116 | Auto | 104; 106; 108FS+1 week |  | 2 months | 2014-10-29 08:00 | 2014-12-23 17:00 | 0 |  | 0% | 0
110 |  | 7.2.3 | Mount PMTs | 40 days | 22 | Auto | 105; 108SS+1 week |  | 2 months | 2014-09-03 08:00 | 2014-10-28 17:00 | 0 |  | 0% | 0
111 |  | 7.2.4 | Mount PMTs, 2nd half | 40 days | 27 | Auto | 105; 109SS+1 week |  | 2 months | 2014-11-05 08:00 | 2014-12-30 17:00 | 0 |  | 0% | 0
112 |  | 7.3 | Test Scintillator |  | 121 | Auto |  |  | 2.25 months | 2014-09-10 08:00 | 2014-11-11 17:00 | 0 |  | 0% | 0
113 |  | 7.3.1 | Test First half | 1 month | 100 | Auto | 110SS+1 week |  | 1 month | 2014-09-10 08:00 | 2014-10-07 17:00 | 0 |  | 0% | 0
114 |  | 7.3.2 | Test Second half |  | 63 | Auto | 111SS+1 week |  | 0 hours | 2014-11-11 17:00 | 2014-11-11 17:00 | 1 |  | 0% | 0
115 |  | 7.4 | Ship Scintillator |  | 84 | Auto |  |  | 2.25 months | 2014-10-15 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
116 |  | 7.4.1 | Pack first half | 10 days | 70 | Auto | 113FS+1 week |  | 2 weeks | 2014-10-15 08:00 | 2014-10-28 17:00 | 0 |  | 0% | 0
117 |  | 7.4.2 | Pack second half | 10 days | 126 | Auto | 114FS+1 week |  | 2 weeks | 2014-11-19 08:00 | 2014-12-02 17:00 | 0 |  | 0% | 0
118 |  | 7.4.3 | Ship first half | 2 weeks | 106 | Auto | 116 |  | 2 weeks | 2014-10-29 08:00 | 2014-11-11 17:00 | 0 |  | 0% | 0
119 |  | 7.4.4 | First half at PSI |  | 104 | Auto | 118 |  | 0 hours | 2014-11-11 17:00 | 2014-11-11 17:00 | 1 |  | 0% | 0
120 |  | 7.4.5 | Ship second half | 2 weeks | 50 | Auto | 117 |  | 2 weeks | 2014-12-03 08:00 | 2014-12-16 17:00 | 0 |  | 0% | 0
121 |  | 7.4.6 | All Scint at PSI |  | 49 | Auto | 120 |  | 0 hours | 2014-12-16 17:00 | 2014-12-16 17:00 | 1 |  | 0% | 0
122 |  | 8 | GEM |  | 89 | Auto |  |  | 1 week | 2015-03-16 08:00 | 2015-03-20 17:00 | 0 |  | 0% | 0
123 |  | 8.1 | Install for test run |  | 94 | Auto | 15 |  | 1 week | 2015-03-16 08:00 | 2015-03-20 17:00 | 0 |  | 0% | 0
124 |  | 9 | Installation |  | 32 | None |  |  | 1.47 years | 2015-03-23 08:00 | 2016-07-27 17:00 | 0 |  | 0% | 0
125 |  | 9.1 | Install table and GEM | 2 weeks | 83 | Auto | 15; 123 |  | 2 weeks | 2015-03-23 08:00 | 2015-04-03 17:00 | 0 |  | 0% | 0
126 |  | 9.2 | Install for test run | 2 months | 78 | Auto | 25; 30; 41; 49; 94; 100; 125 |  | 2 months | 2015-11-19 08:00 | 2016-01-13 17:00 | 0 |  | 0% | 0
127 |  | 9.3 | Ready for test |  | 124 | Auto | 126 |  | 0 hours | 2016-01-13 17:00 | 2016-01-13 17:00 | 1 |  | 0% | 0
128 |  | 9.4 | Install for final run | 2 months | 35 | Auto | 54; 67; 70; 88; 99; 127 |  | 2 months | 2016-06-02 08:00 | 2016-07-27 17:00 | 0 |  | 0% | 0
129 |  | 10 | NSF Funding |  | 88 | Auto |  |  | 1.09 years | 2014-07-01 08:00 | 2015-07-01 17:00 | 0 |  | 0% | 0
130 |  | 10.1 | Funding Part 1 |  | 41 | Auto |  | 2014-07-01 08:00 | 1 day | 2014-07-01 08:00 | 2014-07-01 17:00 | 0 |  | 0% | 0
131 |  | 10.2 | Funding Part 2 |  | 101 | Auto |  | 2015-07-01 08:00 | 1 day | 2015-07-01 08:00 | 2015-07-01 17:00 | 0 |  | 0% | 0