## Sheet1
WBS 5 | Cryogenic Hydrogen Target | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | Total | Tech | Students | PD
[14 empty] | months on line | months on line | months on line
5.1 | Bring Cryolab to Safe Operating State | 2014-03-01 | 2014-06-01 | Both | 18000 | 5000 | 2000 | Internal University Proposal | GWU | 0 | 25000 | Internal Funding Not Approved | 25000
5.2 | Design Drawings | 2014-03-01 | 2014-07-01 | Labor | 0 | 20000 | 0 | Average Cost to Other Projects | PSI | 0 | 25000 | Need to use another designer | 25000
5.3 | Order Instrumrntation, Hardware, and Monitoring Devices | 2014-07-01 | 2014-09-01 | Both | 135000 | 0 | 2100 | Adjusted Cost based on other recent projects | NSF/DOE | 137100 | 13700 | price fluctuations | 150800
5.3 | Order Cryopump - Cold Head | 2014-07-01 | 2014-09-01 | Equipment | 30000 | 0 | 200 | Internet Price Listings and adjusted cost to other recent projects - asking for quotes | NSF/DOE | 30200 | 6000 | price fluctuations - design variation | 36200
5.3 | Order Components of Motion System | 2014-07-01 | 2014-09-01 | Equipment | 35000 | 0 | 2000 | Adjusted costs from other recent projects | NSF/DOE | 37000 | 7000 | price fluctuations - design variation | 44000
5.3 | Order Material/Supplies for Scattering Chamber, Cell, Target Ladder, Holders and Railings | 2014-07-01 | 2014-09-01 | M&S | 14000 | 0 | 2100 | Adjusted costs from other recent projects | NSF/DOE | 16100 | 3000 | price fluctuations - design variation | 19100
5.4 | Prototype Cells and Cell Holders Machining and Assembly | 2014-09-01 | 2014-11-01 | Labor | 0 | 10000 | 24600 | 200 hrs $50/hrs =$10,000 Machinist ---two months each Tech and Students | NSF/DOE | 34600 | 2000 | price fluctuations - design variation | 36600 | 2 | 4 | 0
5.4 | Build Test Stand Chameber | 2014-09-01 | 2014-11-01 | Labor | 0 | 5000 | 24600 | 100 hrs $50/hrs =$5,000 Machinist ---two months each Tech and Students | NSF/DOE | 29600 | 1000 | price fluctuations - design variation | 30600 | 2 | 4 | 0
5.5 | Pressure, Vacuum, Destructive Tests of Cell Prototypes | 2014-11-01 | 2015-01-01 | Labor | 0 | 0 | 35200 | Two months each for Tech, Postdoc, Students | NSF/DOE | 35200 | 0 |  | 35200 | 2 | 4 | 2
5.6 | Evaluation - Design Modification | 2015-01-01 | 2015-02-01 | Labor | 0 | 0 | 17600 | One month each for Tech, Postdoc, Students | NSF/DOE | 17600 | 0 |  | 17600 | 1 | 2 | 1
5.6 | Prototype of Modified Cells | 2015-02-01 | 2015-03-01 | Labor | 0 | 5000 | 17600 | 100 hrs $50/hrs =$5,000 Machinist ---one month each Tech, Post Doc and Students | NSF/DOE | 22600 | 0 |  | 22600 | 1 | 2 | 1
5.7 | Second Round of Tests - Cold Test of Cells | 2015-03-01 | 2015-04-01 | Labor | 0 | 0 | 17600 | One month each Tech, Post Doc and Students | NSF/DOE | 17600 | 0 |  | 17600 | 1 | 2 | 1
5.7 | Final Review of Design and Modifications | 2015-04-01 | 2015-05-01 | Labor | 0 | 2000 | 17600 | 40 hrs $50/hrs =$2000 Machinist ---one month each Tech, Post Doc and Students | NSF/DOE | 19600 | 0 |  | 19600 | 1 | 2 | 1
5.8 | Construction of Scattering Chamber | 2015-05-01 | 2015-07-01 | Labor | 0 | 10000 | 12300 | 200 hrs $50/hrs =$10,000 Machinist ---one month each Tech and Students | NSF/DOE | 22300 | 3000 | price fluctuations - design variation | 25300 | 1 | 2 | 0
5.8 | Construction of Cells | 2015-05-01 | 2015-07-01 | Labor | 0 | 10000 | 12300 | 200 hrs $50/hrs =$10,000 Machinist ---one month each Tech and Students | NSF/DOE | 22300 | 3000 | price fluctuations - design variation | 25300 | 1 | 2 | 0
5.9 | Tests of Cells and Scattering Chamber | 2015-07-01 | 2015-09-01 | Labor | 0 | 0 | 35200 | Two months each Tech, Post Doc and Students | NSF/DOE | 35200 | 0 |  | 35200 | 2 | 4 | 2
5.9 | Evaluation - Modifications | 2015-09-01 | 2015-10-01 | Labor | 0 | 5000 | 17500 | 100 hrs $50/hrs =$5,000 Machinist ---one month each Tech, Post Doc and Students | NSF/DOE | 22500 | 0 |  | 22500 | 1 | 2 | 1
5.10 | Second Round of Tests of Scattering Chamber and Cells Including motion test and test of emergency conditions | 2015-10-01 | 2015-12-01 | Labor | 0 | 0 | 35200 | Two month each Tech, Post Doc and Students | NSF/DOE | 35200 | 0 |  | 35200 | 2 | 4 | 2
5.11 | Evaluation and Readiness Review | 2015-12-01 | 2016-01-01 | Labor | 0 | 0 | 17600 | One month each Tech, Post Doc and Students | NSF/DOE | 17600 | 0 |  | 17600 | 1 | 2 | 1
5.12 | Construct Boxes for Shipping and Packing | 2016-01-01 | 2016-02-01 | Both | 1000 | 2000 | 12300 | 40 hrs Carpentry Shop -- One month each Tech and Students | NSF/DOE | 15300 | 1000 | price fluctuations - design variation | 16300 | 1 | 2 | 0
5.12 | Shipping, Receiving and Unpacking | 2016-02-01 | 2016-03-01 | Both | 2000 | 0 | 12300 | One month each Tech and Students | NSF/DOE | 14300 | 2000 | price fluctuations | 16300 | 1 | 2 | 0
5.13 | In Situ Assembly and Testing | 2016-03-01 | 2016-04-01 | Labor | 0 | 0 | 17600 | One month each Tech, Post Doc and Students | NSF/DOE | 17600 | 5000 | design variation - unforseen needs | 22600 | 1 | 2 | 1
5.14 | PSI Safety Engineering Review and Modifications to Make Compliant | 2016-04-01 | 2016-05-01 | Labor | 0 | 0 | 17600 | One month each Tech, Post Doc and Students | NSF/DOE | 17600 | 5000 | design variation - unforseen needs | 22600 | 1 | 2 | 1
5.15 | Turn over to PSI | 2016-05-01 | 2016-06-01 | Labor | 0 | 0 | 17600 | One month each Tech, Post Doc and Students | NSF/DOE | 17600 | 0 |  | 17600 | 1 | 2 | 1
[14 empty] | 23 | 46 | 15 | Total labor
[5 empty] | 235000 | 74000 | 370700 |  |  | 634700 | 101700 | Does not include Travel, Fringe and imdirects | 736400 | 20 | 40 | 15
|  |  |  | Equipment -> no IDC | 65000 | FB FT -> | 77662 | <-FB FT 0.26
|  |  |  | M&S -> | 170000 | FB PT -> | 4320 | < -FB Students 0.06 | Total FB | 81982 |  | Including Fringe and IDC -> | 1206136.64
|  |  |  | IDC -> | 88400 | 38480 | 235394.64 |  | Total IC | 362274.64 |  | Estimated Travel + IDC -> directly related to Equiptment Construction | 72960 | Est from NSF Proposal
[5 empty] | 323400 |  | 800556.64
[11 empty] | 25480 | <- IDC Contingency -> | 25480
|  | year 1 | 2 | 3 |  |  |  |  | Total W/O Contingency | 1078956.64
| post-doc | 63600 | 66000 | 68400 |  |  |  |  | Total with Travel W/O Contingency | 1151916.64 | 1177396.64 |  | 1304576.64 | Total with travel and contingency
| tech | 75600 | 79200 | 82800
| gs 1 | 36000 | 36000 | 0 | DAQ
| gs 2 | 36000 | 36000 | 0 | Target | [7 empty] | 6.215% | Percent Contingency
|  | 211200 | 217200 | 151200
|  | post-doc | 5300 | 5500 | 5700
|  | tech | 6300 | 6600 | 6900
|  | gs 1 | 3000 | 3000 | 0
|  | gs 2 | 3000 | 3000 | 0
|  | tech + 1 | 9300 | 18600
|  | tech + 2 | 12300 | 24600
|  | tech +2+pd | 17600 | 35200