Planning for the Electronics v1

Year 1

Day 0:

- get access to money

Day 1:

- request update of all quotes

Day 7:

- Order: First half / all of electronics

Day 120 – 180:

-     Receive delivery of electronics at PSI

-     verify that all electronics are working

Day 181 – 240:

- Work out mounting / power / infrastructure questions in collaboration with PSI

- Mount readout as close to the “final” required positions as possible

- Work out necessary cable routing and lengths

- Ordering of necessary cable lengths and connectors

Day 241-300:

- Prototyping and manufacture of cables necessary for communication between detectors and electronics

- Testing of cables

- Installation of cabling

Day 301 – 365

- Installation of MIDAS software on VME controllers

- Test of the addressing and communication of all aspects of the electronics

- Work on integration of complete DAQ

Year 2

Day 1 -7:

- Update quotes if necessary and place order for remaining electronics

- Continue work on integration of complete DAQ, ensuring synchronization

- Order the RAID array for data storage

Day 120 – 180:

- Receive delivery of electronics

- Verify that all electronics are working

Day 180 – 270:

- Install electronics in final position and complete cabling

- Installation of MIDAS software on remaining VME controllers

- Work on integration of complete DAQ

Day 270 – 365

- Final testing and improvement of the DAQ, ready for complete experiment.

Issues to Consider

- Almost all electronics come from Europe, prices are highly dependent on the EUR / USD exchange rate

- Spreading the cost profile over two years will increase the cost of the electronics in some places.

  - CAEN have currently said we can order over two years at no extra cost, but this depends on making a PO for both years at once – not sure of whether GW will agree to this.

  - The TRB3s do not get cheaper when we buy them all at once, but the PADIWAs do

- If we can do away with the MMCX connectors on the PADIWAs – the PADIWAs get a lot cheaper.  We need to quickly discuss alternatives with Michael Traxler.

- We need to figure out what Rutgers need and when in the way of TRB3 hardwarefor trigger prototyping.