## Sheet1
Trip Types
| per item cost | 1 week | 2 week | 1 month | 2 months |  | 89 | 6 | Electronics & DAQ |  | 2010-07-01 08:00 | 2012-05-31 17:00
Flight | 1300 | 1300 | 1300 | 1300 | 1300 |  | 90 | 6.1 | Order first half electronics | 6 months | 2010-07-01 08:00 | 2010-12-15 17:00
Hotel | 100 | 600 | 1400 | 3100 | 6200 |  | 91 | 6.2 | Mounting/order cables | 2 months | 2010-12-16 08:00 | 2011-02-09 17:00
Food | 60 | 420 | 840 | 1860 | 3720 |  | 92 | 6.3 | Manufacture/Install cables | 2 months | 2011-02-10 08:00 | 2011-04-06 17:00
Misc | 300 | 300 | 300 | 300 | 300 |  | 93 | 6.4 | Install and test complete DAQ | 2 months | 2011-04-07 08:00 | 2011-06-01 17:00
Total |  | 2620 | 3840 | 6560 | 11520 |  | 94 | 6.5 | Order 2nd half electronics | 6 months | 2011-07-01 08:00 | 2011-12-15 17:00
[7 empty] | 95 | 6.6 | Install and complete DAQ | 3 months | 2011-12-16 08:00 | 2012-03-08 17:00
[7 empty] | 96 | 6.7 | Final test of DAQ | 3 months | 2012-03-09 08:00 | 2012-05-31 17:00
Year 1
2014-06-14 | C beam test / mounting discussions | 6.2 | ED & Student | 2*2 weeks | 7680
2014-12-14 | Mounting / measuring | 6.2 | ED & Stud. | 2*2 weeks | 7680
|  |  | PD | 1* 1 month | 6560
2014-01-15 | collab@ PSI |  | All | 3* 1 week | 7860
15 (Feb - April) | Cable Manufacture & Install | 6.3 | PD | 1* 2 months | 11520
| UG working at GW, ED & Stud transport |  | ED & Stud | 4*2 weeks | 15360
15 (Apr - June) | install & test | 6.4 | PD | 1*2month | 11520
|  |  | ED & Stud. | 2* 1 month | 13120
Year 2 | [5 empty] | 81300
15 Nov / Dec | Dress Rehersal |  | PD | 1* 2 month | 11520
|  |  | ED & Stud | 4* 2 weeks | 15360
2014-01-16 | Collab @ PSI |  | All | 3* 1 week | 7860
16 Jan - Mar | Install & Complete DAQ | 6.6 | PD | 1* 2 months | 6560
|  |  | ED & Stud | 4* 2 weeks | 15360
Mar - May | Final test of DAQ | 6.7 | All | 6* 2 weeks | 23040
July | Check integration after trigger |  | All | 3* 2 weeks | 11520
91220
Year 3
| Running |  | ED & Stud | 8* 2 weeks | 30720
| Jan 17 collab |  | All | 3* 1 week | 7860
| DAQ testing & checking before run |  | All | 3* 2 week | 11520
| Running Expert |  | PD | 3* 1 month | 19680
Year 4 | [5 empty] | 69780
| Running |  | All | 8* 2 weeks | 30720
| Jan 18 collab |  | All | 3* 1 week | 7860
| Running Expert |  | PD | 3* 1 month | 19680
58260
Total direct | [5 empty] | 300560
Total Indirect | 52% |  |  |  |  | 156291.2
Total | [5 empty] | 456851.2