## Sheet1
WBS 7 | Scintillator Production | start date | end date | M&S or Labor | Cost | BOE
7.1 | Scintillator Purchase
7.1.1 | Order first half | order date | delivery date |  |  | Need quote/catalog value
7.1.2 | Order second half
7.1.3 | Order PMTs
7.1.4 | Supplies
7.1.5 | Backing structure
7.2 | Scintillator Construction
7.2.1 | Wrapping first half scintillator | 1 week after D4 | X weeks after C10 |  |  | Time per piece, $/hr for labor
7.2.2 | Wrapping second half scintillator
7.2.3 | Mounting phototubes | 2 weeks after C10
7.3 | Scintillator Testing |  |  |  |  | also need quality criteria
7.3.1 | Test first half | 1 week after C12
7.3.2 | Test Second half
7.4 | Ship scintillator
7.4.1 | Pack scintillator |  |  |  |  | cost of packing and labor
7.4.2 | Ship first half | shipped first pieces | last pieces arrive |  |  | cost of shipping
7.4.3 | Ship second half