## WBS
WBS 7 | Scintillator Production | start date | duration (d) | end date | M&S or Labor | Cost | BOE
7.1 | Design
7.1.1 | Adopt FTOF design for SC Walls | 2014-04-01 | 5 | 2014-04-08 | Labor | Group's grant
7.1.2 | Adopt FTOF design for beam monitor | 2014-04-08 | 5 | 2014-04-15 | Labor | Group's grant
7.1.3 | New design for veto detector | 2014-04-15 | 14 | 2014-05-05 | Labor | Group's grant
7.1.4 | Milestone: final geometry approved by MUSE council | 2014-05-05
7.2 | Procurement
7.2.1 | Coordinate with university purchasing departement, prepare solicitations and awards | 2014-06-01 | 60 | 2014-07-31
7.2.2 | Order scintillators | 2014-07-31 | 50 | 2014-09-19 | M&S | 78539.76
7.2.3 | Order PMTs | 2014-07-31 | 50 | 2014-09-19 | M&S | 187272
7.2.4 | Order Supplies | 2014-07-31 | 20 | 2014-08-20 | M&S | 18057.6
7.2.5 | Order Backing Structure | 2015-05-01 | 50 | 2015-06-20 | M&S | 44215.2 | 328084.56
7.2.6 | Order Shipping Crates | 2015-05-01 | 20 | 2015-05-21 | M&S | 4788
7.3. | Receiving
7.3.1 | Receive scintillators | 2014-09-19
7.3.2 | Receive PMTs | 2014-09-19
7.3.3 | Receive Supplies | 2014-08-20
7.3.4 | Receive Backing Structure | 2015-06-20
7.3.5 | Receive Shipping Crates | 2015-05-21
7.4 | Construction
7.4.1 | Test and gain determination of PMTs | 2014-09-19 | 30 | 2014-10-30 | Labor | 6538.0978
7.2.2 | beam monitor (two batches) | 2014-10-30 | 40 | 2014-12-25 | Labor | 8542.0348
7.2.3 | veto detector (one batch) | 2014-12-25 | 40 | 2015-02-19 | Labor | 4271.0174
7.2.4 | batch-01 of TOF wall bars | 2015-02-19 | 30 | 2015-04-02 | Labor | 4271.0174
7.2.5 | batch-02 of TOF wall bars | 2015-04-02 | 30 | 2015-05-14 | Labor | 4271.0174
7.2.6 | batch-03 of TOF wall bars | 2015-05-14 | 9 | 2015-05-27 | Labor | 4271.0174
7.2.7 | batch-04 of TOF wall bars | 2015-05-27 | 9 | 2015-06-09 | Labor | 4271.0174
7.2.8 | batch-05 of TOF wall bars | 2015-06-09 | 9 | 2015-06-22 | Labor | 4271.0174
7.2.9 | batch-06 of TOF wall bars | 2015-06-22 | 9 | 2015-07-05 | Labor | 4271.0174
7.2.10 | batch-07 of TOF wall bars | 2015-07-05 | 9 | 2015-07-16 | Labor | 4271.0174
7.2.11 | batch-08 of TOF wall bars | 2015-07-16 | 9 | 2015-07-29 | Labor | 4271.0174 | (one wall finished)
| Milestone: veto, beam-monitor, and one wall ready for shippment | 2015-07-29
7.2.12 | batch-09 of TOF wall bars | 2015-07-29 | 9 | 2015-08-11 | Labor | 4271.0174
7.2.13 | batch-10 of TOF wall bars | 2015-08-11 | 20 | 2015-09-08 | Labor | 4271.0174
7.2.14 | batch-11 of TOF wall bars | 2015-09-08 | 20 | 2015-10-06 | Labor | 4271.0174
7.2.15 | batch-12 of TOF wall bars | 2015-10-06 | 20 | 2015-11-03 | Labor | 4271.0174
7.2.16 | batch-13 of TOF wall bars | 2015-11-03 | 20 | 2015-12-01 | Labor | 4271.0174
7.2.17 | batch-14 of TOF wall bars | 2015-12-01 | 20 | 2015-12-29 | Labor | 4271.0174
7.2.18 | batch-15 of TOF wall bars | 2015-12-29 | 20 | 2016-01-26 | Labor | 4271.0174
7.2.19 | batch-16 of TOF wall bars | 2016-01-26 | 20 | 2016-02-23 | Labor | 4271.0174 | 81149.3311
| Milestone: second wall ready for shippment | 2016-02-23
7.5 | Shipping
7.5.1 | Pack scintillator | [5 empty] | cost of packing and labor
7.5.2 | Ship first half | 2015-07-29 | 10 | 2015-08-12 | M&S | 14364 | cost of shipping
7.5.3 | Ship second half | 2016-02-23 | 10 | 2016-03-08 | M&S | 14364
7.6 | Installation at PSI
7.6.1 | First trip to PSI to install detectors | 2015-08-12 |  |  | M&S | 8724.8
7.6.2 | Second trip to PSI to install detectors | 2016-03-08 |  |  | M&S | 8724.8
[5 empty] | TOTAL | 466737.5888 | only including installation trips
Formulas:
end date = WORKDAY([start date],[duration (d)])
end date = [start date]+[duration (d)]
start date = [end date, row above]

## Budget
Cost Estimate for MUSE SC Wall
SC bars in the front wall | 18 | 184
SC bars in the back wall | 28 | 46
SC bars for beamline | 6
SC wedges for veto | 8
|  | Tax | 8%
Hardware | [5 empty] | first shipment |  | second shipment
Item | QTY | Description | Unit Price USD | Total Price USD | Incl. Tax | QTY | Total USD | QTY | Total USD
1 | 36 | BC-404, 2cm x 6cm x 112cm | 350 | 12600 | 13608 | 18 | 6804 | 18 | 6804
2 | 56 | BC-404, 6cm x 6cm x 211cm | 1019 | 57064 | 61629.12 | 28 | 30814.56 | 28 | 30814.56
3 | 6 | BC-404, 1cm x 6cm x 36cm | 215 | 1290 | 1393.2 | 6 | 1393.2 | 0 | 0
4 | 8 | BC-404, Wedge 6cm x 10cm | 221 | 1768 | 1909.44 | 8 | 1909.44 | 0 | 0
|  | Total |  | 72722 | 78539.76 |  | 40921.2 |  | 37618.56
|  | Contingency | 16% |  | 12566.3616 |  | 6547.392 |  | 6018.9696
5 | 204 | Hamamatsu R9779 | 850 | 173400 | 187272 | 112 | 102816 | 92 | 84456
|  | Contingency | 7% |  | 13109.04 |  | 7197.12 |  | 5911.92
6 | 106 | Supply (glue, foil, wrapping, rubber, tape) | 100 | 10600 | 11448 | 60 | 6480 | 46 | 4968
7 | 204 | Stopper (PMT to SC connection) | 30 | 6120 | 6609.6 | 112 | 3628.8 | 92 | 2980.8
|  | Total |  | 16720 | 18057.6 |  | 10108.8 |  | 7948.8
|  | Contingency | 19% |  | 3430.944 |  | 1920.672 |  | 1510.272
8 | 46 | Backing structure (SC support to be connected to the frame) | 890 | 40940 | 44215.2 | 23 | 22107.6 | 23 | 22107.6
|  | Contingency | 21% |  | 9285.192 | 4.83 | 4642.596 | 4.83 | 4642.596
|  | Total |  |  | 328084.56 |  | 175953.6 |  | 152130.96
|  | Contingency |  |  | 38391.5376 |  | 20307.78 |  | 18083.7576
Item
1 | 2 | Front TOF Wall | 47790 | 95580 | 103226.4
2 | 2 | Back TOF Wall | 93072 | 186144 | 201035.52
3 | 1 | Beam Monitor | 12450 | 12450 | 13446
4 | 1 | Veto Detector | 9608 | 9608 | 10376.64
|  | Total |  | 303782 | 328084.56
Personnel
No of batches | 19 | 6 scintillators per batch |  |  |  | 11 |  | 8
Time/batch | 9 | days |  |  |  | 9 |  | 9
Workers (UG students) | 2 |  |  |  |  | 2 |  | 2
| 8 | h/day |  |  |  | 8 |  | 8
Total hours worked | 1368 | h per student |  |  |  | 792 | h | 576 | h
Compensation | 12 | 1/h
UG Compensation total | 32832
Graduate student base salary | 23000
Fringe rate | 8.29%
Fringe total | 4628.4728
Sub total | 60460.4728
Indirect cost | 19951.956 | 33% on campus training and service
GS Tuition | 485 | per credit hour
Credit hours | 15 |  | Total hours on project | 2736 | hours
Tuition total | 7275 |  | Hours for PMT test | 1 | h/ PMT
|  |  | Total for PMT test | 204 | hours
Total | 87687.4288
Contingency | 9645.6172 | 11%
|  |  | Cost of PMT test | 6538.0978
|  |  | Cost for construction | 4271.0174
|  |  | Total cost pre batch | 4615.1278
Travel
|  | Flight+local transport/person | 1500
|  | Lodging/person/day | 100
|  | Meals/person/day | 60
|  | Visa | 100
Item | QTY | Description | Days | Unit Price USD | Total Price USD
1 | 2 | Detector installation and commissioning | 31 | 6560 | 13120
2 | 4 | Collaboration meetings | 6 | 2460 | 9840
3 | 4 | Expert | 31 | 6560 | 26240
4 | 14 | Two-week experiment shifts | 14 | 3840 | 53760
|  | Sub total |  |  | 102960
|  | Indirect cost |  | 33% | 33976.8
|  | Total |  |  | 136936.8
|  | Contingency |  | 11% | 15063.048
Shipping
Box | 3600 | Estimate for 2 crates (incl. tax)
Shipping to PSI | 10800 | 2 boxes, approx. 50 scintillators each, 700 kg each
Shipping to PSI | 10800 | 2 boxes, approx. 50 scintillators each, 700 kg each
Sub-total | 25200
Indirect cost | 8316 | 33%
Total | 33516
Contingency | 7038.36 | 21%
Indirect Cost
Personnel, Shipping, Travel | 188620.4728
Indirect rate | 33% | on campus training and service
Indirect Cost | 62244.756
TOTAL | 586224.7888
Total without non installation trips | 466737.5888
Description | Year 1 | Year 2 | Year 3 | Year 4 | Total
Equipment | 175953.6 | 152130.96 | 0 | 0 | 328084.56
Personnel | 30230.2364 | 30230.2364 | 0 | 0 | 60460.4728
Travel-1 | 0 | 13120 | 0 | 0 | 13120
Travel-2 | 2460 | 2460 | 2460 | 2460 | 9840
Travel-3 | 0 | 0 | 26880 | 26880 | 53760
Travel-4 | 0 | 0 | 13120 | 13120 | 26240
Travel (total) | 2460 | 15580 | 42460 | 42460 | 102960
Shipping | 0 | 14400 | 0 | 10800 | 25200
Tuition | 3637.5 | 3637.5 | 0 | 0 | 7275
Indirect cost (base) | 32690.2364 | 60210.2364 | 42460 | 53260 | 188620.4728
Indirect cost | 10787.778 | 19869.378 | 14011.8 | 17575.8 | 62244.756
TOTAL | 223069.1144 | 235848.0744 | 56471.8 | 70835.8 | 586224.7888