## Sheet1
WBS 8 | GEM detectors | start date | end date | M&S or Labor | Cost | BOE
8.1 | Purchase of spare electronics
8.1.1 | Order 2 VME crates | 2014-07-01 | 2014-10-01 | Equipment | 14464 | Quote/previous order
8.1.2 | Order 2 VME CPUs | 2014-07-01 | 2014-10-01 | Equipment | 6170 | Quote/previous order
8.1.3 | Order 2 MPDs | 2014-07-01 | 2014-10-01 | Equipment | 6300 | Quote
8.1.4 | Supplies for cabeling and connectors | 2014-07-01 | 2014-10-01 | Supplies | 1500 | Estimated
8.2 | Establish fast readout
8.2.1 | Commission new electronics | 1 week after D6 | 2 weeks after C9 |  |  | Time per piece
8.2.2 | Make cables | 1 week after D6 | 4 weeks after C9
8.2.3 | Test combined system | 1 week after D10 | 4 weeks after C11
8.3 | Ship 2 crates | 1 week after D11 | 4 weeks after C12 |  | 2000 | estimated / previous shipment
| Total |  |  |  | 30434