## Sheet1
SciFi | start date | end date | M&S or Labor | Cost | F&A | Contingency | Total w/o contingency | BOE
8 PMTs |  |  |  | 22741.7476 | 0 | 2274.1748 | 22741.7476 | Quote | 292800 Yen/each | 2842.7184 | Contingency based on 10% currency fluctuation
Send out orders for SciFi, WLS Fibers, PMTs | 2014-07-31 | 2015-01-27 | M&S | 31700 | 4755 | 7291 | 36455 | Estimate |  |  | 20% contingency
Design mounting structures | 2014-07-31 | 2014-09-29 | Labor |  |  | 0 | 0 | Estimate
Order cutting/polishing tools | 2014-07-31 | 2014-09-29 | M&S | 15000 | 2250 | 3450 | 17250 | Quotes |  |  | 20% cotingency
Design Bases + Electronics | 2014-07-31 | 2014-09-29 | Both |  |  |  |  | E-Shop | From non NSF/DOE Sources
Prototype construction | 2015-02-01 | 2015-03-03 | Labor
Construct fibers | 2015-03-01 | 2015-05-30 | Labor
Machine frames | 2015-04-01 | 2015-05-01 | Labor
Mount Fibers | 2015-06-01 | 2015-07-01 | Labor
Commisioning tests at TAU | 2015-07-01 | 2015-07-31 | Labor
Shipping to PSI | 2015-08-01 | 2015-08-31 | Labor
Tests at PSI (Beam + Cosmics) | 2015-09-01 | 2015-10-31 | Labor
Total M&S |  |  |  | 69441.7476 | 7005 | 13015.1748 | 76446.7476
Labor |  |  |  | 70000 | 10500 | 16100 | 80500
total |  |  |  | 139441.7476 | 17505 | 29115.1748 | 156946.7476
Labor |  | F&A | Contingency | 20%
Technician year 1 | 15000 | 2250 | 3450
year 2 | 5000 | 750 | 1150
GS year 1 | 25000 | 3750 | 5750
GS year 2 | 25000 | 3750 | 5750
| 70000 | 10500 | 16100
Formulas:
end date = [start date]+180