## Sheet1
WBS | WBS | Item | Risk | Probability | Impact |  |  |  | Remedy
| sub item |  |  |  | Cost | Time | Scope | Quality
1 | 1.1 | Support Table | Design is preliminary, cost increase, added design time | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
| 1.3 | Scintillator frame | Design is preliminary, cost increase, added design time | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
| 1.4 | Beam monitor frame | Design is preliminary, cost increase, added design time | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
2 | 2.1.1 | Order fiber | cost increase | 0.3 | 0.2 | 0.05 | 0.05 | 0.05
| 2.1.2 | Order PMT | cost increase | 0.3 | 0.2 | 0.05 | 0.05 | 0.05
|  |  | Doesn't meet efficiency or timing specs. | 0.3 | 0.2 | 0.05 | 0.1 | 0.1
3 | 3.3 | Cerenkov | Doesn't meet specs | 0.2 | 0.2 | 0.1 | 0.05 | 0.1
4 | 4.1 | Order materials | cost increase | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
| 4.5 | Chamber mount | cost increase | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
| 4.9 | Chamber 1 | takes too long to build | 0.3 | 0.2 | 0.2 | 0.05 | 0.05
| 4.14 | Chamber 2-4 | takes too long to build | 0.3 | 0.2 | 0.2 | 0.05 | 0.05
5 | 5.3 | Order major elements | cost increase | 0.3 | 0.2 | 0.05 | 0.05 | 0.05
| 5.4 | Construct prototype | Unable to find qualified tech | 0.2 | 0.4 | 0.2 | 0.05 | 0.05
| 5.5 | test of prototype | failure of prototype | 0.3 | 0.2 | 0.4 | 0.05 | 0.05
| 5.11 | test complete system | failure of system | 0.1 | 0.2 | 0.2 | 0.05 | 0.05
6 | 6.1 | Order electronics | cost increase | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
| 6.4 | Develop DAQ | extra time to develop DAQ | 0.3 | 0.4 | 0.4 | 0.1 | 0.05
| 6.7 | Order 2nd half electronics | cost increase | 0.3 | 0.2 | 0.1 | 0.05 | 0.05
7 | 7.2 | Materials for Scintillator | cost increase | 0.3 | 0.2 | 0.05 | 0.05 | 0.05
| 7.3 | Construction | takes longer than expected | 0.3 | 0.2 | 0.05 | 0.05 | 0.05
8 | 8.1 | Order electronics | cost increase | 0.3 | 0.2 | 0.2 | 0.05 | 0.05
| 8.4 | Test system | unable to get speed needed | 0.5 | 0.4 | 0.4 | 0.2 | 0.2