## Sheet1 - Table 1
WBS 3 | Beam Cerenkov part | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | F&A | Total Equipment only | Contingency equipment only
3.1 | Design frame for 1st Cerenkov | 2014-04-01 | 2015-09-01 | Labor | 0 |  |  | existing manpower | NSF/DOE | 0 |  |  |  | 0
3.2 | beam test of Photek, Photonis | 2014-06-15 | 2014-06-30 | travel - $6,000 asked separately |  |  |  | recent experience for 1 1-week + 1 2-week trips | NSF/DOE | 0 | 300 | recent experience for trip costs variations |  | 0
3.2 | Order first 4 Photek MCP-PMT 240’s | 2014-08-01 | 2014-12-01 | Equipment | 87600 |  |  | Photek quote, 1/24/2014 | NSF / DOE | 87600 | 8760 | 10% based on currency fluctuations |  | 87600 | 8760
3.3 | Order sapphire bars | 2014-08-01 | 2014-11-01 | Equipment | 5050 |  |  | DelMar Photonics quote, 2/6/14 | NSF / DOE | 5050 | 505 | 10% based on currency fluctuations | 1414 | 6464 | 505
3.4 | Order 5 mounting fixtures | 2014-09-01 | 2014-10-01 | Equipment | 125 |  |  | purchase of 3d printed mounting fixture in October 2013 | NSF/DOE | 125 | 2500 | contingency is for machined mounting fixtures |  | 125 | 2500
3.5 | Supplies | 2014-09-01 | 2014-10-01 | Labor | 0 |  |  | all existing, do not expect to need | NSF/DOE | 0 | 100 | In case electrical tape or optical grease or ... needed... |  | 0 | 100
3.6 | Construct frame for 1st prototype | 2014-09-01 | 2014-11-30 | parts & labor | 1000 | 2000 |  | Estimate based on crude design, to produce in Rutgers machine shop | NSF/DOE | 3000 | 1000 | Only crude design exists, not costed by machine shop | 840 | 1840 | 1000
3.7 | Test of available equipment at PSI | 2014-12-01 | 2014-12-20 | Travel - $3,500 asked separately |  |  |  | recent experience for 2-week trips to Switzerland | NSF/DOE | 0 | 300 | recent experience for trip costs variations |  | 0 | 0
3.8 | Order first 5 more Photek MCP-PMT 240’s | 2015-08-01 | 2015-12-01 | Equipment | 107500 |  |  | Photek quote, 1/24/2014 | NSF/DOE | 107500 | 10750 |  |  | 107500 | 10750
3.9 | Order 5 mounting fixtures | 2015-09-01 | 2015-10-01 | parts | 125 |  |  | purchase of 3d printed mounting fixture in October 2013 | NSF/DOE | 125 | 2500 | contingency is for machined mounting fixtures |  | 125 | 2500
3.10 | Dress rehearsal run at PSI | 2015-11-01 | 2015-12-20 | Travel - $7,000 asked separatrly |  |  |  | recent experience for 2 2-week trips to Switzerland | NSF/DOE | 0 | 600 | recent experience for trip costs variations |  | 0 | 0
3.11 | Data analysis | 2015-11-01 | 2016-02-01 |  | 0 |  |  | existing manpower | [5 empty] | 0 | 0
3.12 | Design frame for 2nd Cerenkov | 2016-02-01 | 2016-04-01 | Labor | 0 |  |  |  | NSF/DOE | 0 |  |  |  | 0 | 0
3.13 | Construct frame for 2nd prototype | 2016-04-01 | 2016-05-01 | parts & labor | 1000 | 2000 |  | Estimate based on crude design, to produce in Rutgers machine shop | NSF/DOE | 3000 | 1000 |  | 840 | 1840 | 1000
3.14 | install Cerenkov at PSI and commission | 2016-05-01 | 2016-06-01 | Travel - $7,000 asked separately |  |  |  | recent experience for 2 2-week trips to Switzerland | NSF/DOE | 0 | 600 | recent experience for trip costs variations |  | 0
[13 empty] | 3094 | 205494 | 27115
NOTES:
3.1) Manuel Schwarz, PSI might design, build, and do controls
| 3.2) Opportunity: Use Photonis Planacon in place of Photek PMT-240 - planning to test in June 2014 - will reduce MCP costs to about $112,000 | Have 1 Photek, with 4 more can instrument enough of IFP + target for dress reheasal
3.3) Using Planacon in 3.1 will change sapphire sizes but not affect overall cost much
3.4) 3d printed plastic - might decide to go with machined metal mount for better positioning
3.5) already have tape, optical greases, gloves, cleaning supplies
3.7) preplanned test time