## Sheet1
WBS 5 | Cryogenic Hydrogen Target | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE (labor is max estimated requirement for task) | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | Total
5.1 | Bring Cryolab to Safe Operating State | 2014-03-01 | 2014-06-01 | Both | 18000 | 5000 | 2000 | Internal University Proposal | GWU | 0 | 25000 | Internal Funding Not Approved | 25000
5.1.1 | Design Drawings | 2014-03-01 | 2014-07-01 | Labor | 0 | 20000 | 0 | Average Cost to Other Projects | PSI | 0 | 25000 | Need to use another designer | 25000
5.1.2 | Order Instrumentation, Hardware, and Monitoring Devices | 2014-07-01 | 2014-09-01 | Both | 135000 | 0 |  | Adjusted Cost based on other recent projects | NSF/DOE | 135000 | 35100 | price fluctuations | 170100
5.1.3 | Order Cryopump - Cold Head | 2014-07-01 | 2014-09-01 | Equipment | 30000 | 0 |  | Internet Price Listings and adjusted cost to other recent projects - asking for quotes | NSF/DOE | 30000 | 7800 | price fluctuations - design variation | 37800
5.1.4 | Order Components of Motion System | 2014-07-01 | 2014-09-01 | Equipment | 35000 | 0 |  | Adjusted costs from other recent projects | NSF/DOE | 35000 | 9100 | price fluctuations - design variation | 44100
5.1.5 | Order Material/Supplies for Scattering Chamber, Cell, Target Ladder, Holders and Railings | 2014-07-01 | 2014-09-01 | M&S | 14000 | 0 |  | Adjusted costs from other recent projects | NSF/DOE | 14000 | 3640 | price fluctuations - design variation | 17640
5.1.6 | Prototype Cells and Cell Holders Machining and Assembly | 2014-09-01 | 2014-11-01 | Labor | 0 | 10000 |  | 200 hrs $50/hrs =$10,000 Machinist ---two months each Tech and Students | NSF/DOE | 10000 | 2600 | price fluctuations - design variation | 12600
5.1.7 | Build Test Stand Chameber | 2014-09-01 | 2014-11-01 | Labor | 0 | 5000 |  | 100 hrs $50/hrs =$5,000 Machinist ---two months each Tech and Students | NSF/DOE | 5000 | 1300 | price fluctuations - design variation | 6300
5.1.8 | Pressure, Vacuum, Destructive Tests of Cell Prototypes | 2014-11-01 | 2015-01-01 | Labor | 0 | 0 |  | Two months each for Tech, Postdoc, Students | NSF/DOE | 0 | 0 |  | 0
5.1.9 | Evaluation - Design Modification | 2014-01-01 | 2015-02-01 | Labor | 0 | 0 |  | One month each for Tech, Postdoc, Students | NSF/DOE | 0 | 0 |  | 0
5.1.10 | Prototype of Modified Cells | 2015-02-01 | 2015-03-01 | Labor | 0 | 5000 |  | 100 hrs $50/hrs =$5,000 Machinist ---one month each Tech, Post Doc and Students | NSF/DOE | 5000 | 1300 |  | 6300
5.1.11 | Second Round of Tests - Cold Test of Cells | 2015-03-01 | 2015-04-01 | Labor | 0 | 0 |  | One month each Tech, Post Doc and Students | NSF/DOE | 0 | 0 |  | 0
5.1.13 | Final Review of Design and Modifications | 2015-04-01 | 2015-05-01 | Labor | 0 | 2000 |  | 40 hrs $50/hrs =$2000 Machinist ---one month each Tech, Post Doc and Students | NSF/DOE | 2000 | 460 |  | 2460
5.1.14 | Construction of Scattering Chamber | 2015-05-01 | 2015-07-01 | Labor | 0 | 10000 |  | 200 hrs $50/hrs =$10,000 Machinist ---one month each Tech and Students | NSF/DOE | 10000 | 2600 | price fluctuations - design variation | 12600
5.2.1 | Construction of Cells | 2015-05-01 | 2015-07-01 | Labor | 0 | 10000 |  | 200 hrs $50/hrs =$10,000 Machinist ---one month each Tech and Students | NSF/DOE | 10000 | 2600 | price fluctuations - design variation | 12600
5.2.2 | Tests of Cells and Scattering Chamber | 2015-07-01 | 2015-09-01 | Labor | 0 | 0 |  | Two months each Tech, Post Doc and Students | NSF/DOE | 0 | 0 |  | 0
5.2.3 | Evaluation - Modifications | 2015-09-01 | 2015-10-01 | Labor | 0 | 5000 |  | 100 hrs $50/hrs =$5,000 Machinist ---one month each Tech, Post Doc and Students | NSF/DOE | 5000 | 1150 |  | 6150
5.2.4 | Second Round of Tests of Scattering Chamber and Cells Including motion test and test of emergency conditions | 2015-10-01 | 2015-12-01 | Labor | 0 | 0 |  | One month each Tech, Post Doc and Students | NSF/DOE | 0 | 0 |  | 0
5.2.5 | Evaluation and Readiness Review | 2015-12-01 | 2016-01-01 | Labor | 0 | 0 |  | One month each Tech, Post Doc and Students | NSF/DOE | 0 | 0 |  | 0
5.2.6 | Construct Boxes for Shipping and Packing | 2016-01-01 | 2016-02-01 | Both | 1000 | 2000 |  | 40 hrs Carpentry Shop -- One month each Tech and Students | NSF/DOE | 3000 | 780 | price fluctuations - design variation | 3780
5.2.7 | Shipping, Receiving and Unpacking | 2016-02-01 | 2016-03-01 | Both | 2000 | 0 |  | One month each Tech and Students | NSF/DOE | 2000 | 520 | price fluctuations | 2520
5.2.8 | In Situ Assembly and Testing | 2016-03-01 | 2016-04-01 | Labor | 0 | 0 |  | One month each Tech, Post Doc and Students | NSF/DOE | 0 | 0 | design variation - unforseen needs | 0
5.2.9 | PSI Safety Engineering Review and Modifications to Make Compliant | 2016-04-01 | 2016-05-01 | Labor | 0 | 0 |  | One month each Tech, Post Doc and Students | NSF/DOE | 0 | 0 | design variation - unforseen needs | 0
5.3 | Turn over to PSI | 2016-05-01 | 2016-06-01 | Labor | 0 | 0 |  | One month each Tech, Post Doc and Students | NSF/DOE | 0 | 0 |  | 0
|  |  |  | cost to project | 217000 | 49000 | 2000 |  |  | 266000 | 118950 | Does not include Travel, Fringe and imdirects | 384950
|  |  |  | Equipment -> no IDC | 65000 |  | Total Labor | 386428
|  |  |  | M&S -> | 152000 |  | F&A on Labor | 192593
|  |  |  | IDC -> | 79040 |  | Contingency on labor | 97733
|  |  |  | total M&S | 217000
|  |  |  | total external labor | 74000 |  | total f&A | 271633
|  |  |  | F&A on ext | 38480 |  | total cont. | 216683