## Sheet1
WBS 6 | Electronics & DAQ | start date | end date | M&S or Labor | M & S & E Cost | External Skilled Paid Labor | Emplyee / Student | BOE | Funding Source | Cost to Sponsor | Contingency | Reason for Contingency | Total
6.1 | Order first half of electronics | 2014-06-01 | 2014-12-01 | Labor & Equipment | 195514 |  |  | CAEN & GSI Quotes | NSF / DOE | 195514 | 33237 | EUR / USD exchange + loss of CAEN discount + possibly having to buy more expensive crates | 228751
6.2 | Organisation of mounting / power / infrastructure issues at PSI | 2014-03-01 | 2014-09-01 | Labor |  |  |  |  | NSF / DOE | 0 |  |  | 0
6.3 | Work on DAQ drivers & readout to improve speed | 2014-07-01 | 31-Jun-2016 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.4 | Receive delivery of electronics at PSI, and verify functionality | 2014-12-01 | 2015-03-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.5 | Mounting of electronics in "final" positions | 2015-02-01 | 2015-04-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.6 | Planning, prototyping and ordering cable components | 2015-04-01 | 2015-06-01 | L & E | 10800 |  | 0 | Estimates based on catalogue parts costs | NSF/DOE | 10800 | 2000 | Changing connector requirements / exchange rate estimates | 12800
6.7 | Cable manufacture, testing & installation, mounting on table where appropriate | 2015-06-01 | 2015-09-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.8 | Installation of DAQ software & integration of complete DAQ to read out all components. | 2015-08-01 | 2015-10-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.9 | Update quotes and place orders for remaining electronics | 2015-06-01 | 2015-08-01 | Labor | 118914 |  |  | CAEN & GSI Quotes | NSF/DOE | 118914 | 26161 | EUR / USD exchange + loss of CAEN discount + possibly having to buy more expensive crate | 145075
6.10 | Update quotes & place order for RAID array | 2015-06-01 | 2015-08-01 | Labor | 88291 |  |  | DELL Quote | NSF/DOE | 88291 | 10595 | 10% fluctuation due to price change / increased storage need | 98886
6.11 | Receive delivery of electronics & RAID Array at PSI, and verify functionality | 2015-12-01 | 2016-03-01 | Labor & Equipment |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.12 | Install electronics in final position and complete cabling | 2016-03-01 | 2016-04-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.13 | Install software and complete integration of new DAQ components | 2016-04-01 | 2016-05-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
6.14 | Final testing & improvement of DAQ software | 2016-05-01 | 2016-07-01 | Labor |  |  |  |  | NSF/DOE | 0 |  |  | 0
[10 empty] | 413519 | 71993 |  | 485512
Labor
[9 empty] | Salaries | 165996
[9 empty] | F&A | 86318
[9 empty] | Contingency | 25231
[9 empty] | total contingecy | 97224
[13 empty] | #DIV/0! | Percent Contingency